## README
ARIS — Personal Tracker
Owner: Anass · Build window: May 4 – Aug 31, 2026 · Placement sprint: Sept – Nov 2026
TABS IN THIS WORKBOOK
1. Pre-Day-1 Setup — every download, account, and physical prep before May 4. Tick as you go.
2. Daily Log — one row per day. Hours worked, what got done, blockers, mood. Fills LOG.md by exporting column D.
3. Weekly Review — every Sunday evening, 30 min. Score the week, list wins/blockers, plan next week.
4. Phase Milestones — 'Done means' checklist for every phase. The definition of phase complete.
5. Success Metrics — the 5 dimensions from ARIS-SUCCESS-CRITERIA.md. Floor/Target/Stretch with live status.
6. Tier A B C Grafts — the 2026-04-29 grafts that move the plan from 7 to 9. Tier A+B is mandatory.
7. Applications — every placement application. Company, role, date, status, follow-up.
8. LinkedIn Outreach — Brunel alumni at F1 firms. 30/60/90 names. Sent / replied / call booked.
9. Mock Interviews — recorded reps. Date, question, self-score, lessons.
10. Learning Resources — courses, books, papers. Status, hours invested, certificate y/n.
11. Risks — risk register. Likelihood, impact, mitigation, status.
12. GitHub Cadence — commit count per week vs target (>=4/wk).
13. Brunel Racing — engagement log. Messages sent, replies, meetings, data path.
14. Tools and Accounts — every tool installed, account created, license status.
RULES
- Update Daily Log every evening before sleep. 5 minutes max.
- Update Weekly Review every Sunday evening before the next week starts.
- If a row is red for two consecutive weeks, the plan changes — escalate, don't endure.
- This sheet is the single source of truth for progress. The plan docs describe intent; this sheet describes reality.
STATUS COLOURS
- Green (Done / On track) — task complete or floor metric cleared.
- Yellow (In progress / At risk) — actively working OR close to floor.
- Red (Blocked / Missed) — not happening on current trajectory; needs intervention.
- Grey (Not started / N/A) — not begun or no longer applicable.
QUICK LINKS (relative paths from this folder)
- ARIS-FINAL-PLAN.md — strategic plan
- ARIS-EXECUTION-PLAN.md — week-by-week operational plan (with Pre-Day-1 setup)
- ARIS-SUCCESS-CRITERIA.md — what 'done' means in numbers
- ARIS-IMPROVEMENT-SYNTHESIS.md — why the plan was revised on 2026-04-29
- Deep Research Answers/ — the 4 AI reviewer outputs

## Pre-Day-1 Setup
Pre-Day-1 Setup
Every download, account, and physical prep. Finish by Sun May 3 evening. Day 1 = May 4.
Category | Item | Where / how | Status | Notes
Software | Python 3.11 via pyenv-win | winget install pyenv-win; pyenv install 3.11.9 | Not started
Software | uv (Astral) | winget install --id=astral-sh.uv | Not started | Faster than pip
Software | Git for Windows | git-scm.com | Not started
Software | GitHub CLI (gh) | winget install GitHub.cli; gh auth login | Not started
Software | VS Code | code.visualstudio.com | Not started
Software | VS Code extensions: Python, Pylance, Ruff, Jupyter, Docker, GitLens, Mermaid, Markdown All-in-One | Extensions panel | Not started
Software | Docker Desktop | docker.com/products/docker-desktop | Not started
Software | NVIDIA driver (latest Game Ready / Studio) | nvidia.com | Not started | Verify with nvidia-smi
Software | CUDA Toolkit 12.x | developer.nvidia.com/cuda-downloads | Not started | Verify with nvcc --version
Software | Ollama | ollama.com | Not started
Software | Llama 3.1 8B q5 model | ollama pull llama3.1:8b-instruct-q5_K_M | Not started | ~5.5 GB
Software | Llama 3.2 3B fallback | ollama pull llama3.2:3b | Not started | If 8B is tight on VRAM
Software | DBeaver Community (optional) | dbeaver.io | Not started | Postgres GUI
Software | OBS Studio | obsproject.com | Not started | Phase 7 demo recording
Software | DaVinci Resolve free or CapCut | blackmagicdesign.com | Not started | Phase 7 video edit
Software | MATLAB Online or student license | matlab.mathworks.com | Not started | Tier B graft, Wks 11–12
Software | Excel / LibreOffice Calc | Already installed | Done | For this tracker
Account | GitHub profile cleaned (NeuroSim removed) | github.com/AnassNadeem | Not started | Profile README rewrite
Account | Streamlit Community Cloud | share.streamlit.io | Not started | Sign in with GitHub
Account | Neon.tech free Postgres tier | neon.tech | Not started | Save connection string
Account | Hugging Face | huggingface.co | Not started | Tier C — Spaces deployment
Account | MathWorks | mathworks.com | Not started | MATLAB Online + Onramp
Account | Coursera (Andrew Ng + Michigan VD audit) | coursera.org | Not started | Audit free
Account | LinkedIn profile updated to ARIS framing | linkedin.com | Not started
Account | Bright Network newsletter | brightnetwork.co.uk | Not started | F1 placement event alerts
Account | Anthropic Console (defer) | console.anthropic.com | Not started | Only for Phase 6 polish
Account | Groq (Tier C fallback) | console.groq.com | Not started | Cloud LLM fallback
Account | YouTube channel ready | youtube.com | Not started | For unlisted demo video
Account | Medium account | medium.com | Not started | Blog posts in Phases 6–7
Physical | Borrow Rajamani — Vehicle Dynamics and Control | Brunel library — reserve early | Not started | Wk5 read
Physical | Borrow Milliken — Race Car Vehicle Dynamics | Brunel library | Not started | Phase 7 interview prep
Physical | Brunel Racing contact name + role identified | MEng friend / team page | Not started | Day 1 WhatsApp depends on this
Physical | Brunel Careers Service first 1:1 booked | brunel.ac.uk/life/careers | Not started | Sometime in May
Physical | Mock-interview friend identified | Personal network | Not started
Repo | aris repo created (public, MIT, .gitignore) | gh repo create AnassNadeem/aris | Not started | Empty Wk1 Day 1
Repo | aris-matlab-validation repo created | gh repo create | Not started | For Tier B graft Wks 11–12
Repo | Profile README rewritten (template in execution plan) | github.com/AnassNadeem/AnassNadeem | Not started | Done before first commit
Repo | Pinned repos reordered (ARIS #1, hackathons #2-3) | Pin from profile | Not started
Repo | Profile photo + location London + bio set | GitHub settings | Not started
Cache | FastF1 cache pre-pulled for 2023+2024 (10 races overnight) | Python script in Pre-Day-1 §E | Not started | Avoids Wk2 stall
Drafts | WhatsApp message to Brunel Racing drafted | Plain text file, sends Day 1 morning | Not started | From ARIS-FINAL-PLAN §4
Drafts | Leakage-test pytest scaffold drafted | 30 lines, commits Phase 2 Day 1 | Not started | Most important commit

## Daily Log
Daily Log
One row per day, May 4 → Aug 31. Update every evening, 5 min max.
Date | Day | Phase | Hours | What got done (1-2 lines, exportable to LOG.md) | Blockers | Mood (1-5) | Tomorrow's first task
2026-05-04 | Mon | Phase 0 — Python + FastF1
2026-05-05 | Tue | Phase 0 — Python + FastF1
2026-05-06 | Wed | Phase 0 — Python + FastF1
2026-05-07 | Thu | Phase 0 — Python + FastF1
2026-05-08 | Fri | Phase 0 — Python + FastF1
2026-05-09 | Sat | Phase 0 — Python + FastF1
2026-05-10 | Sun | Phase 0 — Python + FastF1 |  | REST DAY (non-negotiable per plan §5)
2026-05-11 | Mon | Phase 0 — Python + FastF1
2026-05-12 | Tue | Phase 0 — Python + FastF1
2026-05-13 | Wed | Phase 0 — Python + FastF1
2026-05-14 | Thu | Phase 0 — Python + FastF1
2026-05-15 | Fri | Phase 0 — Python + FastF1
2026-05-16 | Sat | Phase 0 — Python + FastF1
2026-05-17 | Sun | Phase 0 — Python + FastF1 |  | REST DAY (non-negotiable per plan §5)
2026-05-18 | Mon | Phase 1 — Postgres + Streamlit
2026-05-19 | Tue | Phase 1 — Postgres + Streamlit
2026-05-20 | Wed | Phase 1 — Postgres + Streamlit
2026-05-21 | Thu | Phase 1 — Postgres + Streamlit
2026-05-22 | Fri | Phase 1 — Postgres + Streamlit
2026-05-23 | Sat | Phase 1 — Postgres + Streamlit
2026-05-24 | Sun | Phase 1 — Postgres + Streamlit |  | REST DAY (non-negotiable per plan §5)
2026-05-25 | Mon | Phase 1 — Postgres + Streamlit
2026-05-26 | Tue | Phase 1 — Postgres + Streamlit
2026-05-27 | Wed | Phase 1 — Postgres + Streamlit
2026-05-28 | Thu | Phase 1 — Postgres + Streamlit
2026-05-29 | Fri | Phase 1 — Postgres + Streamlit
2026-05-30 | Sat | Phase 1 — Postgres + Streamlit
2026-05-31 | Sun | Phase 1 — Postgres + Streamlit |  | REST DAY (non-negotiable per plan §5)
2026-06-01 | Mon | Phase 2 — Lap-time predictor
2026-06-02 | Tue | Phase 2 — Lap-time predictor
2026-06-03 | Wed | Phase 2 — Lap-time predictor
2026-06-04 | Thu | Phase 2 — Lap-time predictor
2026-06-05 | Fri | Phase 2 — Lap-time predictor
2026-06-06 | Sat | Phase 2 — Lap-time predictor
2026-06-07 | Sun | Phase 2 — Lap-time predictor |  | REST DAY (non-negotiable per plan §5)
2026-06-08 | Mon | Phase 2 — Lap-time predictor
2026-06-09 | Tue | Phase 2 — Lap-time predictor
2026-06-10 | Wed | Phase 2 — Lap-time predictor
2026-06-11 | Thu | Phase 2 — Lap-time predictor
2026-06-12 | Fri | Phase 2 — Lap-time predictor
2026-06-13 | Sat | Phase 2 — Lap-time predictor
2026-06-14 | Sun | Phase 2 — Lap-time predictor |  | REST DAY (non-negotiable per plan §5)
2026-06-15 | Mon | Phase 2 — Lap-time predictor
2026-06-16 | Tue | Phase 2 — Lap-time predictor
2026-06-17 | Wed | Phase 2 — Lap-time predictor
2026-06-18 | Thu | Phase 2 — Lap-time predictor
2026-06-19 | Fri | Phase 2 — Lap-time predictor
2026-06-20 | Sat | Phase 2 — Lap-time predictor
2026-06-21 | Sun | Phase 2 — Lap-time predictor |  | REST DAY (non-negotiable per plan §5)
2026-06-22 | Mon | Phase 3 — Counterfactual
2026-06-23 | Tue | Phase 3 — Counterfactual
2026-06-24 | Wed | Phase 3 — Counterfactual
2026-06-25 | Thu | Phase 3 — Counterfactual
2026-06-26 | Fri | Phase 3 — Counterfactual
2026-06-27 | Sat | Phase 3 — Counterfactual
2026-06-28 | Sun | Phase 3 — Counterfactual |  | REST DAY (non-negotiable per plan §5)
2026-06-29 | Mon | Phase 3 — Counterfactual
2026-06-30 | Tue | Phase 3 — Counterfactual
2026-07-01 | Wed | Phase 3 — Counterfactual
2026-07-02 | Thu | Phase 3 — Counterfactual
2026-07-03 | Fri | Phase 3 — Counterfactual
2026-07-04 | Sat | Phase 3 — Counterfactual
2026-07-05 | Sun | Phase 3 — Counterfactual |  | REST DAY (non-negotiable per plan §5)
2026-07-06 | Mon | Phase 4 — Always-on loop
2026-07-07 | Tue | Phase 4 — Always-on loop
2026-07-08 | Wed | Phase 4 — Always-on loop
2026-07-09 | Thu | Phase 4 — Always-on loop
2026-07-10 | Fri | Phase 4 — Always-on loop
2026-07-11 | Sat | Phase 4 — Always-on loop
2026-07-12 | Sun | Phase 4 — Always-on loop |  | REST DAY (non-negotiable per plan §5)
2026-07-13 | Mon | Phase 4 — Always-on loop
2026-07-14 | Tue | Phase 4 — Always-on loop
2026-07-15 | Wed | Phase 4 — Always-on loop
2026-07-16 | Thu | Phase 4 — Always-on loop
2026-07-17 | Fri | Phase 4 — Always-on loop
2026-07-18 | Sat | Phase 4 — Always-on loop
2026-07-19 | Sun | Phase 4 — Always-on loop |  | REST DAY (non-negotiable per plan §5)
2026-07-20 | Mon | Phase 4.5 — Monte Carlo
2026-07-21 | Tue | Phase 4.5 — Monte Carlo
2026-07-22 | Wed | Phase 4.5 — Monte Carlo
2026-07-23 | Thu | Phase 4.5 — Monte Carlo
2026-07-24 | Fri | Phase 5 — LLM narration
2026-07-25 | Sat | Phase 5 — LLM narration
2026-07-26 | Sun | Phase 5 — LLM narration |  | REST DAY (non-negotiable per plan §5)
2026-07-27 | Mon | Phase 5 — LLM narration
2026-07-28 | Tue | Phase 5 — LLM narration
2026-07-29 | Wed | Phase 5 — LLM narration
2026-07-30 | Thu | Phase 5 — LLM narration
2026-07-31 | Fri | Phase 5 — LLM narration
2026-08-01 | Sat | Phase 5 — LLM narration
2026-08-02 | Sun | Phase 5 — LLM narration |  | REST DAY (non-negotiable per plan §5)
2026-08-03 | Mon | Phase 6 — Eval + demo + conformal
2026-08-04 | Tue | Phase 6 — Eval + demo + conformal
2026-08-05 | Wed | Phase 6 — Eval + demo + conformal
2026-08-06 | Thu | Phase 6 — Eval + demo + conformal
2026-08-07 | Fri | Phase 6 — Eval + demo + conformal
2026-08-08 | Sat | Phase 6 — Eval + demo + conformal
2026-08-09 | Sun | Phase 6 — Eval + demo + conformal |  | REST DAY (non-negotiable per plan §5)
2026-08-10 | Mon | Phase 6 — Eval + demo + conformal
2026-08-11 | Tue | Phase 6 — Eval + demo + conformal
2026-08-12 | Wed | Phase 6 — Eval + demo + conformal
2026-08-13 | Thu | Phase 6 — Eval + demo + conformal
2026-08-14 | Fri | Phase 6 — Eval + demo + conformal
2026-08-15 | Sat | Phase 6 — Eval + demo + conformal
2026-08-16 | Sun | Phase 6 — Eval + demo + conformal |  | REST DAY (non-negotiable per plan §5)
2026-08-17 | Mon | Phase 7 — Apps prep
2026-08-18 | Tue | Phase 7 — Apps prep
2026-08-19 | Wed | Phase 7 — Apps prep
2026-08-20 | Thu | Phase 7 — Apps prep
2026-08-21 | Fri | Phase 7 — Apps prep
2026-08-22 | Sat | Phase 7 — Apps prep
2026-08-23 | Sun | Phase 7 — Apps prep |  | REST DAY (non-negotiable per plan §5)
2026-08-24 | Mon | Phase 7 — Apps prep
2026-08-25 | Tue | Phase 7 — Apps prep
2026-08-26 | Wed | Phase 7 — Apps prep
2026-08-27 | Thu | Phase 7 — Apps prep
2026-08-28 | Fri | Phase 7 — Apps prep
2026-08-29 | Sat | Phase 7 — Apps prep
2026-08-30 | Sun | Phase 7 — Apps prep |  | REST DAY (non-negotiable per plan §5)
2026-08-31 | Mon | Phase 7 — Apps prep

## Weekly Review
Weekly Review
Every Sunday evening, 30 min. Score the week. Honest, not flattering.
Wk # | Week of (Mon) | Phase | Hours target | Hours actual | Wins (≤3) | Blockers (≤3) | Self-score (1-10) | Plan for next week
1 | 2026-05-04 | Phase 0 — Python + FastF1 | 36
2 | 2026-05-11 | Phase 0 — Python + FastF1 | 36
3 | 2026-05-18 | Phase 1 — Postgres + Streamlit | 36
4 | 2026-05-25 | Phase 1 — Postgres + Streamlit | 36
5 | 2026-06-01 | Phase 2 — Lap-time predictor | 36
6 | 2026-06-08 | Phase 2 — Lap-time predictor | 36
7 | 2026-06-15 | Phase 2 — Lap-time predictor | 36
8 | 2026-06-22 | Phase 3 — Counterfactual | 36
9 | 2026-06-29 | Phase 3 — Counterfactual | 36
10 | 2026-07-06 | Phase 4 — Always-on loop | 36
11 | 2026-07-13 | Phase 4 — Always-on loop | 36
12 | 2026-07-20 | Phase 4.5 — Monte Carlo | 36
13 | 2026-07-27 | Phase 5 — LLM narration | 36
14 | 2026-08-03 | Phase 6 — Eval + demo + conformal | 36
15 | 2026-08-10 | Phase 6 — Eval + demo + conformal | 36
16 | 2026-08-17 | Phase 7 — Apps prep | 36
17 | 2026-08-24 | Phase 7 — Apps prep | 36
18 | 2026-08-31 | Phase 7 — Apps prep | 36
19 | 2026-09-07 | Y2 — Apps sprint | 36
20 | 2026-09-14 | Y2 — Apps sprint | 36
21 | 2026-09-21 | Y2 — Apps sprint | 36
22 | 2026-09-28 | Y2 — Apps sprint | 36
23 | 2026-10-05 | Y2 — Apps sprint | 36
24 | 2026-10-12 | Y2 — Apps sprint | 36
25 | 2026-10-19 | Y2 — Apps sprint | 36
26 | 2026-10-26 | Y2 — Apps sprint | 36
27 | 2026-11-02 | Y2 — Apps sprint | 36
28 | 2026-11-09 | Y2 — Apps sprint | 36
29 | 2026-11-16 | Y2 — Apps sprint | 36
30 | 2026-11-23 | Y2 — Apps sprint | 36
31 | 2026-11-30 | Y2 — Apps sprint | 36

## Phase Milestones
Phase Milestones
'Done means' from ARIS-EXECUTION-PLAN.md. Phase isn't done until every box is ticked.
Phase | Deliverable | Target date | Status | Notes
Phase 0 — Python + FastF1 | Public GitHub repo with ≥8 commits, README + screenshot | 2026-05-17 | Not started
Phase 0 | LOG.md with daily bullets | 2026-05-17 | Not started
Phase 0 | Two notebooks committed showing FastF1 working | 2026-05-17 | Not started
Phase 0 | WhatsApp sent (Day 1) | 2026-05-04 | Not started
Phase 0 | Can write Python class without lookup | 2026-05-17 | Not started
Phase 0 | Can do pandas groupby+agg+merge without lookup | 2026-05-17 | Not started
Phase 1 — Postgres + Streamlit | Local Postgres running via docker compose up | 2026-05-31 | Not started
Phase 1 | 10+ races ingested, ≥500k telemetry rows | 2026-05-31 | Not started
Phase 1 | Streamlit app deployed to public URL (Wk3 Day 6 — moved earlier) | 2026-05-24 | Not started
Phase 1 | Statistical baseline (sector moving avg) shipped Wk3 | 2026-05-24 | Not started
Phase 1 | Brunel Racing hard-kill checkpoint (Wk3 Day 5 — moved earlier) | 2026-05-22 | Not started
Phase 1 | Leakage-test pytest scaffold staged for Phase 2 Day 1 | 2026-05-31 | Not started
Phase 1 | First public LinkedIn post with URL | 2026-05-31 | Not started
Phase 2 — Lap-time predictor | tests/test_no_leakage.py committed Day 1, in CI | 2026-06-01 | Not started
Phase 2 | aris.physics.bicycle module with tests + fuel + pit-loss | 2026-06-07 | Not started
Phase 2 | aris.physics.tires module with fit coefficients per compound | 2026-06-14 | Not started
Phase 2 | aris.models.residual predictor with eval results in README | 2026-06-21 | Not started
Phase 2 | Held-out MAE: floor <1.0s achieved (target <0.7s, stretch <0.5s) | 2026-06-21 | Not started
Phase 2 | Can derive bicycle model from Newton's 2nd law on whiteboard | 2026-06-21 | Not started
Phase 3 — Counterfactual | Action vocabulary documented in docs/actions.md | 2026-07-05 | Not started
Phase 3 | Counterfactual page deployed live | 2026-07-05 | Not started
Phase 3 | Demo screenshot captured | 2026-07-05 | Not started
Phase 3 | All public functions have type hints + docstrings | 2026-07-05 | Not started
Phase 4 — Always-on loop | Always-on loop runs without manual prodding | 2026-07-19 | Not started
Phase 4 | Recommendation feed visible and updating | 2026-07-19 | Not started
Phase 4 | Tick latency documented honestly (NOT marketed as feature) | 2026-07-19 | Not started
Phase 4 | Hero GIF in README | 2026-07-19 | Not started
Phase 4.5 — Monte Carlo | Monte Carlo module with seeded reproducibility | 2026-07-23 | Not started
Phase 4.5 | Recommendations now include MC confidence intervals | 2026-07-23 | Not started
Phase 4.7 — MATLAB port | aris-matlab-validation repo created (public, MIT) | 2026-07-26 | Not started
Phase 4.7 | Bicycle outputs agree Python ↔ MATLAB to 5% on 10 stints | 2026-08-02 | Not started
Phase 4.7 | Simulink block diagram present + screenshot | 2026-08-02 | Not started
Phase 4.7 | Repo pinned on GitHub profile (slot #2) | 2026-08-02 | Not started
Phase 5 — LLM narration | Llama 3.1 narration working locally on GPU, <2s/call | 2026-08-02 | Not started
Phase 5 | Ask ARIS pane answers grounded questions correctly | 2026-08-02 | Not started
Phase 5 | Spot-check 20 narrations: ≤2 hallucinated numbers | 2026-08-02 | Not started
Phase 6 — Eval + conformal + demo | Backtest results in README with conformal interval coverage | 2026-08-09 | Not started
Phase 6 | docs/strategy-backtest.md (undercut risk, SC sensitivity, pit deltas) | 2026-08-09 | Not started
Phase 6 | Conformal calibration: empirical coverage 85-95% measured | 2026-08-09 | Not started
Phase 6 | 90-second demo video on YouTube unlisted | 2026-08-16 | Not started
Phase 6 | Blog post #1 (technical) published | 2026-08-09 | Not started
Phase 6 | Can answer 'how did you handle uncertainty?' in 60s | 2026-08-16 | Not started
Phase 7 — Apps prep | CV (1 page) + cover letter template + 11 customised versions | 2026-08-22 | Not started
Phase 7 | 30 LinkedIn alumni identified, message template ready | 2026-08-22 | Not started
Phase 7 | 10 recorded mock-interview answers reviewed | 2026-08-29 | Not started
Phase 7 | 5-min code walkthrough rehearsed without notes | 2026-08-29 | Not started
Phase 7 | Blog post #2 (motivation/story) published | 2026-08-31 | Not started
Phase 7 | Can describe ARIS in 30s, 90s, and 5min | 2026-08-31 | Not started

## Success Metrics
Success Metrics
From ARIS-SUCCESS-CRITERIA.md (revised 2026-04-29). 5 dimensions × Floor / Target / Stretch.
Dimension | Metric | Floor | Target | Stretch | Current
1. Technical | Held-out lap-time MAE (point estimate) | < 1.0s | < 0.7s | < 0.5s | —
1. Technical | Conformal 90% interval coverage | Built, measured | 85–95% empirical | 88–92% + width report | —
1. Technical | Validated races (held-out) | 3 | 5 | 10+ | —
1. Technical | Race-by-race CV harness + leakage test | Day 1 of Phase 2 | + CI test | + negative control | —
1. Technical | Always-on loop tick latency | < 15s | < 5s | < 2s | —
1. Technical | Counterfactual action types | 1 | 5 | 5 + chains | —
1. Technical | Monte Carlo samples in <5s | 100 | 1000 | 10000 | —
1. Technical | Recommendation hit rate | > 50% | > 65% | > 75% | —
1. Technical | LLM narration accuracy (no hallucinated numbers) | ≤2 wrong / 20 | ≤2 / 50 | 0 with structured output | —
1. Technical | Tiered ticks working | Tier 1 + 3 | All 3 + event | All + sub-400ms event | —
1. Technical | Competitor pivot triggers | 1 example | 3 examples | 5+ + auto-flag | —
1. Technical | Ask ARIS grounded answers | 15/20 | 18/20 | 20/20 | —
1. Technical | MATLAB/Simulink validation artefact | Bicycle ports, 5% match | + Simulink + repo | + stint cross-validated | —
1. Technical | Backtest report in strategy language | 1 page PDF | Multi-page tied to 5 races | + recruiter exec summary | —
2. Career | Placement applications submitted | 8 | 15 | 25+ | —
2. Career | First-stage interviews | 2 | 5 | 10+ | —
2. Career | Final-stage interviews | 1 | 3 | 5+ | —
2. Career | Placement offer received | 0 (pipeline healthy) | 1 | 2+ | —
2. Career | LinkedIn alumni messages sent | 30 | 60 | 90+ | —
2. Career | LinkedIn alumni replies | 5 | 12 | 20+ | —
2. Career | Brunel Careers 1:1 sessions | 1 | 3 | 5+ | —
2. Career | Mock interviews completed | 5 | 10 | 15+ | —
2. Career | Recognised courses (audit or cert) | 1 (MATLAB Onramp) | 3 | 4+ inc. paid cert | —
3. Process | Can derive bicycle model on whiteboard | Done from memory ≤10 min | — | — | —
3. Process | Can explain XGBoost vs MLP choice | 1-paragraph reasoned answer | — | — | —
3. Process | Can walk through any src/aris/ file | No 'I'd have to look that up' | — | — | —
3. Process | Can name 3 limitations unprompted | All 3 real | — | — | —
3. Process | Re-derive Phase 2 results on fresh checkout | Runs end-to-end Aug 25 | — | — | —
3. Process | Wrote ≥30% of total LOC by hand | Honest self-check | — | — | —
4. Artefact | GitHub profile cleaned (NeuroSim purged) | Done before Day 1 | — | — | —
4. Artefact | All 4 dashboard modes shipped | Yes | — | — | —
4. Artefact | README pitch in first 3 lines | Yes | — | — | —
4. Artefact | Hero GIF / screenshot above fold | Yes | — | — | —
4. Artefact | 1-command install + run | docker compose up && streamlit run | — | — | —
4. Artefact | Live URL works on phone (mobile network) | Yes | — | — | —
4. Artefact | 90-second demo video on YouTube | Yes | — | — | —
4. Artefact | Repo ≥80 commits | Yes (~5/wk) | — | — | —
4. Artefact | ≥2 blog posts published | 1 technical + 1 motivation | — | — | —
4. Artefact | ≥5 LinkedIn posts during build | Yes | — | — | —
4. Artefact | Code passes ruff + pytest | Yes | — | — | —
5. Brunel Racing (bonus) | Replied to WhatsApp | +1 | — | — | —
5. Brunel Racing (bonus) | Got a meeting/call | +2 | — | — | —
5. Brunel Racing (bonus) | Test-day telemetry access | +3 | — | — | —
5. Brunel Racing (bonus) | Ran ARIS on their data, showed back | +5 | — | — | —
5. Brunel Racing (bonus) | Team adopted any part of ARIS | +8 | — | — | —

## Tier A B C Grafts
Tier A / B / C Grafts (the 7→9 score lift)
From ARIS-IMPROVEMENT-SYNTHESIS.md. Tier A+B mandatory. Tier C only after A+B is locked.
Tier | Graft | Effort | When | Why | Status
A | Recalibrate MAE (floor <1.0s, target <0.7s, stretch <0.5s) | Hours | Pre-Day-1 | Calibrating below silent baseline = credible | Not started
A | Reframe CV target → Software Engineer (Performance/Strategy Tools) | Hours | Pre-Day-1 | Software path is documented; Race Strategy at Y2 is gated to 1 role | Not started
A | GitHub profile cleaned (NeuroSim purged) | 1 hour | Pre-Day-1 (May 3) | First impression / ARIS becomes pinned signal | Not started
A | Brunel Racing severed as dependency, kept as upside | Plan edit | Pre-Day-1 | 6-week dependency was fatal per Gemini | Not started
A | Brunel hard kill moves Wk6 → Wk3 Day 5 | Plan edit | Pre-Day-1 | Same | Not started
A | Physics positioning: 'lightweight + interpretable + LLM-narrated' | README edit | Phase 0 | Don't invite TUMFTM/multi-body comparison | Not started
A | Stop marketing 5s tick latency | README edit | Phase 4 | Real F1 sub-second; 5s is footgun if marketed | Not started
B | Conformal prediction calibration (Phase 6) | ~2 days | Wk14 | Single highest-leverage technical addition | Not started
B | Race-by-race CV + leakage test, Day 1 of Phase 2 | 30 lines | Phase 2 Day 1 | #1 risk per Claude — leakage destroys MAE credibility | Not started
B | MATLAB/Simulink port of bicycle module (separate repo) | ~1 week | Wks 11–12 evenings | Closes Mercedes HPP / RB Powertrains 'good to have' | Not started
B | Phase 1 cloud deploy moves Wk4 → Wk3 | Plan edit | Wk3 | Recovers a week for Phase 2 leakage debug | Not started
B | Statistical baseline by Wk2 (moving avg sector times) | Hours | Wk2 | Lets dashboard ship before ML lands | Not started
B | Pit-stop logic + linear fuel-burn term in physics layer | Hours | Wk5 | Widens scope to F1-strategy-reviewer expectation | Not started
B | Backtest report in strategy language (docs/strategy-backtest.md) | 1 day | Wk14 | Different language for different audience | Not started
C | Hugging Face Spaces deployment | 1 day | Wk16 if locked | Free CV signal | Not started
C | Llama 3.2 3B fallback if 8B is tight on VRAM | 4 hrs | Wk13 | Mitigates Gemini's OOM risk | Not started
C | Groq free tier as cloud LLM fallback | 2 hrs | Wk13 | Removes Ollama as SPOF | Not started
C | pybind11 C++ Monte Carlo inner loop | 3–4 days | Y2 only if needed | Don't pre-optimise | Not started
C | 1× LeetCode-easy block per week | 2 hrs/wk | Throughout | Software placement screens are auto-graded | Not started
C | 5 canonical strategy interview questions drilled | 5×30 min | Wks 16–17 | Bernie Collins canonical set | Not started
C | Public Kaggle/HF dataset of FastF1 backtest task | 1 day | Y2 | Own the benchmark | Not started
C | Brunel Racing in-person test-day visit | 1 day | Wk8 or Wk9 | Public viewing — they don't have to invite you | Not started
C | Toastmasters / mock-interview reps for English fluency | 2 hrs/wk | Y2 | Cadence not vocabulary | Not started
C | Submit to AIcrowd / Kaggle motorsport competitions | Varies | Y2 | Free CV signal | Not started
C | Blog post #3 on conformal prediction in F1 strategy | 1 day | Y2 | Niche-defining | Not started

## Applications
Placement Applications
Target: 15 submitted by Nov 30, 2026. 8 floor / 25+ stretch.
# | Company | Role | Date submitted | Portal / link | Status | Last action | Next action | Notes
1 | McLaren | Engineering Placement (Software / Vehicle Performance) |  |  | Not started
2 | Williams | Vehicle Engineering Industrial Placement |  |  | Not started
3 | Williams | Technology & Innovation Industrial Placement |  |  | Not started
4 | Williams | Vehicle Performance Software placement |  |  | Not started
5 | Red Bull Racing | Industrial Student Placement (Software) |  |  | Not started
6 | Red Bull Racing | Race Strategy Student Placement (long-shot stretch) |  |  | Not started
7 | Red Bull Powertrains | Industrial Placement (Software/Controls) |  |  | Not started
8 | Mercedes AMG HPP | Software & Controls 12-Month Placement |  |  | Not started
9 | Mercedes AMG HPP | Engineering Placement 2027 |  |  | Not started
10 | Mercedes Petronas F1 | Software Engineering Placement |  |  | Not started
11 | Aston Martin F1 | Software Placement |  |  | Not started
12 | Aston Martin Performance Technologies (AMPT) | Vehicle Performance Software |  |  | Not started
13 | Alpine F1 | Software / Strategy Placement |  |  | Not started
14 | M-Sport | Engineering / Software Placement |  |  | Not started
15 | Williams Advanced Engineering | Software Placement |  |  | Not started
16 | Red Bull Advanced Technologies | Software Placement |  |  | Not started
17 | AP Racing | Engineering Placement |  |  | Not started
18 | Stray Systems | Software Placement |  |  | Not started
19 | Bentley Motors | Vehicle Performance Placement |  |  | Not started
20 | Cosworth | Engineering Placement |  |  | Not started
21 | M-Sport (rally-adjacent) | Software |  |  | Not started
22 | Cadillac F1 (new entry) | Software / Strategy Placement |  |  | Not started

## LinkedIn Outreach
LinkedIn Outreach
Brunel alumni at F1/motorsport firms. Floor 30 / Target 60 / Stretch 90. 3 messages/week (Mon/Wed/Fri).
# | Name | Company | Role | Brunel link | Date contacted | Replied? | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Mock Interviews
Mock Interviews
Floor 5 / Target 10 / Stretch 15+. Record on phone, watch back, cringe, re-do.
# | Date | Question / topic | Self-score (1-10) | Lesson / what to fix | Re-recorded?
1 |  | Walk me through a pit stop from a strategy perspective
2 |  | Why is undercut faster than overcut sometimes?
3 |  | Explain gap-to-leader vs gap-to-car-ahead in strategic terms
4 |  | 1-stop vs 2-stop in changing weather — how do you decide?
5 |  | Describe a time you used data to defend a decision under pressure
6 |  | Walk me through ARIS in 30 seconds
7 |  | Walk me through ARIS in 5 minutes
8 |  | How did you handle uncertainty? (conformal prediction)
9 |  | Why physics+residual vs pure ML?
10 |  | What are the limitations of ARIS?
11 |  | Why XGBoost over a sequence model?
12 |  | Derive the bicycle model from Newton's 2nd law
13 |  | Why is this not a world model?
14 |  | Why no reinforcement learning?
15 |  | How would you handle real-time telemetry at 1ms latency?

## Learning Resources
Learning Resources
Courses, books, papers. Status / hours invested / cert? Drop the course not the build.
Resource | Type | Why (which gap it fills) | Hours target | Hours actual | Status
CS50P (Harvard Python) | Course | Phase 0 Python foundations | 10 | 0 | Not started
Boot.dev — Learn Python | Course | Phase 0 alt | 12 | 0 | Not started
James Powell — Pandas From The Ground Up | Tutorial | Phase 0 pandas | 3 | 0 | Not started
Kaggle — Pandas micro-course | Course | Phase 0 pandas exercises | 4 | 0 | Not started
FastF1 official docs | Docs | Phase 0 ingest | 3 | 0 | Not started
SQLBolt | Course | Phase 1 SQL | 2 | 0 | Not started
PostgreSQL Tutorial — sections 1–5 | Docs | Phase 1 Postgres | 4 | 0 | Not started
Streamlit 30 Days | Course | Phase 1 Streamlit | 8 | 0 | Not started
SQLAlchemy 2.0 Unified Tutorial 1–6 | Docs | Phase 1 ORM | 3 | 0 | Not started
Rajamani — Vehicle Dynamics Ch.2 | Book (library) | Phase 2 bicycle model | 8 | 0 | Not started
Pacejka Wikipedia + simplified form | Reference | Phase 2 tire model | 1 | 0 | Not started
scikit-learn user guide §1.1, 3.1, 3.3 | Docs | Phase 2 ML basics | 4 | 0 | Not started
XGBoost Python tutorial | Docs | Phase 2 residual | 3 | 0 | Not started
PyTorch — Learn the Basics | Course | Phase 2 MLP | 3 | 0 | Not started
Frontiers 2025 — Deep learning for F1 pit stops | Paper | Phase 2 reference | 2 | 0 | Not started
TUM race-simulation README + racesim_basic | Code | Wk5 reference | 4 | 0 | Not started
RealPython type hints | Tutorial | Phase 3 API design | 1 | 0 | Not started
Pydantic v2 docs | Docs | Phase 3 actions | 2 | 0 | Not started
RealPython async IO walkthrough | Tutorial | Phase 4 loop | 2 | 0 | Not started
Brandon Foltz — Monte Carlo intuition | Video | Phase 4.5 MC | 1 | 0 | Not started
MATLAB Onramp (free, MathWorks) | Course | Tier B graft + CV line | 2 | 0 | Not started
Simulink Onramp (free, MathWorks) | Course | Tier B graft | 2 | 0 | Not started
MATLAB for Data Processing & Visualization | Course | MATLAB CV line | 5 | 0 | Not started
Andrew Ng ML Specialization (audit) | Course | Theory + ML CV line | 30 | 0 | Not started
Michigan Vehicle Dynamics specialisation (audit) | Course | Vehicle dynamics CV line | 20 | 0 | Not started
MIT 6.86x ML with Python (audit, optional) | Course | Alt to Andrew Ng | 25 | 0 | Not started
Anastasios Angelopoulos — Conformal Prediction (Gentle Intro) | Paper | Phase 6 conformal | 3 | 0 | Not started
mapie Python library docs | Docs | Phase 6 conformal impl | 2 | 0 | Not started
Anthropic — Prompt Engineering Overview | Docs | Phase 5 LLM | 2 | 0 | Not started
Milliken — Race Car Vehicle Dynamics (library, ref) | Book (library) | Phase 7 interview prep | 6 | 0 | Not started
NeetCode 150 — easy section | Course | Tier C — Software interview screens | 15 | 0 | Not started
Bernie Collins — How to Win a Grand Prix | Book | Tier C — strategy interview prep | 6 | 0 | Not started
Atlassian Git tutorials (branches, merge, rebase) | Docs | Phase 0 Git | 2 | 0 | Not started
MIT OCW 18.06 Linear Algebra (no cert) | Course | Foundation, optional | 30 | 0 | Not started

## Risks
Risk Register
Live risk tracking. Mitigation, owner, status. Update weekly.
# | Risk | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Status
1 | Train/test leakage in Phase 2 produces inflated MAE | 4 | 5 | 20 | Race-by-race CV harness + leakage unit test committed Day 1 of Phase 2 | Open
2 | FastF1 cache failures / API rate limits stall Wk1–2 | 3 | 3 | 9 | Pre-pull cache overnight May 3; budget a full debug day Wk2 | Open
3 | Postgres on Windows via Docker breaks (volumes/networking) | 3 | 3 | 9 | Stick to Postgres 16 base, named volumes not bind mounts, no extensions | Open
4 | Streamlit cold-start makes Neon free tier feel broken | 3 | 3 | 9 | 5-min keepalive ping via GitHub Action | Open
5 | Llama 3.1 8B + XGBoost + Streamlit OOMs on 8GB VRAM | 3 | 4 | 12 | Tier C: Llama 3.2 3B fallback, Groq cloud fallback | Open
6 | Phase 2 lap-time MAE > 1.5s on held-out | 3 | 4 | 12 | Drop residual MLP, ship physics-only with conformal intervals; honest is better than over-claim | Open
7 | Phase 4 tick latency cannot hit 5s | 2 | 2 | 4 | Loosen to 15s, document tradeoff; do not sink a week on pre-optimisation | Open
8 | Brunel Racing never replies / no data | 4 | 2 | 8 | Severed as dependency Wk3 Day 5; story pivots to held-out FastF1 + sim telemetry | Open
9 | English fluency under interview pressure | 3 | 4 | 12 | Tier C Toastmasters reps; record mocks; address directly in cover letter | Open
10 | F1 hiring contraction (budget cap effects) | 2 | 3 | 6 | Apply F1-adjacent: M-Sport, Cosworth, Bentley, Williams Advanced Engineering | Open
11 | Project feels generic vs other FastF1 visualisers | 2 | 4 | 8 | Lead with conformal-calibrated counterfactuals + LLM narration — unbuilt elsewhere | Open
12 | Course-collecting eats build time | 3 | 3 | 9 | Drop the course not the build; audit-only; max 3 courses parallel | Open
13 | Demo video takes >5 days to record | 3 | 2 | 6 | Ship 60-second version if 90s blocks; done > perfect | Open
14 | GitHub graph stays sparse despite plan | 3 | 3 | 9 | Daily commits including learning notebooks; weekly review checks count | Open
15 | Health / personal crisis | 2 | 5 | 10 | Buffer weeks at end; keep Brunel adviser updated; cut scope not deadline | Open
16 | Over-claiming on README damages credibility | 3 | 5 | 15 | Calibrated targets (<1.0/<0.7/<0.5); conformal intervals; honest backtest | Open
17 | Wrong target role (Race Strategy vs Software) | 3 | 5 | 15 | Reframed Pre-Day-1 to Software Engineer (Performance/Strategy Tools) | Open
18 | Hardware/CAN issues on Brunel Racing data delay ML | 4 | 4 | 16 | Fixed by Wk3 Day 5 kill; not waiting 6 weeks | Open

## GitHub Cadence
GitHub Cadence
Target ≥4 commits/week (Mon–Sat counts; Sunday off). ARIS repo + MATLAB validation repo combined.
Wk # | Week of (Mon) | Commits ARIS | Commits MATLAB | Total | Target | Hit?
1 | 2026-05-04 |  |  | 0 | 4 | No
2 | 2026-05-11 |  |  | 0 | 4 | No
3 | 2026-05-18 |  |  | 0 | 4 | No
4 | 2026-05-25 |  |  | 0 | 4 | No
5 | 2026-06-01 |  |  | 0 | 4 | No
6 | 2026-06-08 |  |  | 0 | 4 | No
7 | 2026-06-15 |  |  | 0 | 4 | No
8 | 2026-06-22 |  |  | 0 | 4 | No
9 | 2026-06-29 |  |  | 0 | 4 | No
10 | 2026-07-06 |  |  | 0 | 4 | No
11 | 2026-07-13 |  |  | 0 | 4 | No
12 | 2026-07-20 |  |  | 0 | 4 | No
13 | 2026-07-27 |  |  | 0 | 4 | No
14 | 2026-08-03 |  |  | 0 | 4 | No
15 | 2026-08-10 |  |  | 0 | 4 | No
16 | 2026-08-17 |  |  | 0 | 4 | No
17 | 2026-08-24 |  |  | 0 | 4 | No
18 | 2026-08-31 |  |  | 0 | 4 | No
19 | 2026-09-07 |  |  | 0 | 4 | No
20 | 2026-09-14 |  |  | 0 | 4 | No
21 | 2026-09-21 |  |  | 0 | 4 | No
22 | 2026-09-28 |  |  | 0 | 4 | No
23 | 2026-10-05 |  |  | 0 | 4 | No
24 | 2026-10-12 |  |  | 0 | 4 | No
25 | 2026-10-19 |  |  | 0 | 4 | No
26 | 2026-10-26 |  |  | 0 | 4 | No
27 | 2026-11-02 |  |  | 0 | 4 | No
28 | 2026-11-09 |  |  | 0 | 4 | No
29 | 2026-11-16 |  |  | 0 | 4 | No
30 | 2026-11-23 |  |  | 0 | 4 | No
31 | 2026-11-30 |  |  | 0 | 4 | No

## Brunel Racing
Brunel Racing engagement log
Severed as dependency Wk3 Day 5. Kept as upside. Update on every interaction.
Date | Channel | Interaction (sent / received / met) | Outcome | Next step
2026-05-04 | WhatsApp | First message sent (template from ARIS-FINAL-PLAN §4) | — | Wait 7 days
(One polite follow-up if no reply by 2026-05-11)
2026-05-22 | Decision | Wk3 Day 5 hard-kill checkpoint — keep as upside or drop

## Tools and Accounts
Tools and Accounts (live register)
Every tool installed, account created, license/expiry. Quick reference when something breaks.
Tool / account | Type | Username / handle | Expiry / cost | Status | Notes
GitHub | Account | AnassNadeem | Free | Active | Profile cleaned pre-Day-1
Streamlit Community Cloud | Account | (via GitHub) | Free | — | Set up pre-Day-1
Neon.tech Postgres | Account | — | Free 3GB | — | Connection string in .env
Hugging Face | Account | — | Free | — | Tier C — Spaces
Coursera | Account | — | Free audit | — | Andrew Ng + Michigan VD
MathWorks | Account | — | Free Online | — | MATLAB + Onramp
Anthropic Console | Account | — | Pay-as-you-go | Defer | Phase 6 polish only
Groq | Account | — | Free tier | — | Tier C fallback
Bright Network | Account | — | Free | — | F1 placement event alerts
LinkedIn | Account | — | Free | Active | Profile updated to ARIS framing
Medium | Account | — | Free | — | Blog posts
YouTube | Account | — | Free | — | Unlisted demo video
Ollama | Tool | — | Free | — | Local LLM
Docker Desktop | Tool | — | Free for personal | —
CUDA Toolkit | Tool | — | Free | — | 12.x
VS Code | Tool | — | Free | —
MATLAB Online | Tool | — | Free tier | — | Or student license via Brunel
OBS Studio | Tool | — | Free | — | Phase 7
DaVinci Resolve free | Tool | — | Free | — | Phase 7
Brunel library — Rajamani | Physical | — | Loan | — | Reserve early
Brunel library — Milliken | Physical | — | Loan | —
Brunel Careers Service 1:1 | Service | — | Free | — | Book ≥3