## Dashboard
ARIS Master Planner — Dashboard
Auto-updating from Daily Log, ARIS Tasks, DSA, Resources, Applications, Networking
[6 empty] | Chart Data: Phase Completion |  |  | Chart Data: Time Allocation (this week) |  | Chart Data: DSA Patterns Done |  | Chart Data: Application Funnel
Days to ARIS Ship | Days to Apps Open | ARIS Tasks Done | ARIS % | DSA Solved | Apps Submitted | Phase | Done | Total | Category | Hours | Pattern | Done | Stage | Count
116 | 131 | 10 | 8.929% | 0 | 0 | Phase 0 | 10 | 21 | ARIS | 0 | Arrays & Hashing | 0 | Applied+ | 0
[6 empty] | Phase 1 | 0 | 13 | DSA | 0 | Two Pointers | 0 | OA Stage+ | 0
Hours This Week | Hours Target Wk | Resources Done | Network Replies | Outreach Sent | Offers | Phase 2 | 0 | 12 | App Tool | 0 | Sliding Window | 0 | Phone+ | 0
0 | 36 | 0 | 0 | 0 | 0 | Phase 3 | 0 | 18 | Networking | 0 | Stack | 0 | Final+ | 0
[6 empty] | Phase 4 | 0 | 9 | Writing | 0 | Binary Search | 0 | Offers | 0
[6 empty] | Phase 5 | 0 | 9 | Resources | 0 | Linked List | 0
[6 empty] | Phase 6 | 0 | 9 | Other | 0 | Trees | 0
[6 empty] | Phase 7 | 0 | 11 |  |  | Tries | 0
[6 empty] | Phase 8 | 0 | 10 |  |  | Heap | 0
[11 empty] | Backtracking | 0
[11 empty] | Graphs | 0
[11 empty] | Advanced Graphs | 0
[11 empty] | 1-D DP | 0
[11 empty] | 2-D DP | 0
[11 empty] | Greedy | 0
[11 empty] | Intervals | 0
[11 empty] | Math & Geometry | 0
[11 empty] | Bit Manipulation | 0
Current Week Focus
Week # | 1
Phase | Phase 1 — Python found.
Theme | Day 1 ignition: Python, Boot.dev OOP, NumPy, repo init
Tasks This Week | 6 | Done | 0 | % Complete | 0%
Hours Logged | 0 | DSA Done | 0 | DSA Target | 5
Quick navigation
→ Daily Log: log hours every evening (60 seconds).
→ ARIS Tasks: tick to Done as you finish each task. Charts above auto-update.
→ DSA Tracker: log every problem; the by-pattern chart shows your coverage gaps.
→ Resources: when you finish a course, set Status = Done and log hours.
→ Applications: pre-populated with target list; fire from Sept 15 onwards.
→ Networking: log every outreach + reply. Stale follow-ups (>14d) flag red.

## Weekly Overview
Week | Phase | Start | End | Theme | ARIS Tasks Total | ARIS Tasks Done | ARIS % | DSA Target | DSA Done | Hours Logged | Status
0 | Phase 0 — Pre-flight | 2026-04-29 | 2026-05-03 | Setup: tools, accounts, GitHub purge, Day 1 readiness | 21 | 10 | 47.62% | 0 | 0 | 0 | Past Due
1 | Phase 1 — Python found. | 2026-05-04 | 2026-05-10 | Day 1 ignition: Python, Boot.dev OOP, NumPy, repo init | 6 | 0 | 0% | 5 | 0 | 0 | Current
2 | Phase 1 — Python found. | 2026-05-11 | 2026-05-17 | pandas + first FastF1 plot, statistical baseline | 7 | 0 | 0% | 5 | 0 | 0 | Future
3 | Phase 2 — Pipeline | 2026-05-18 | 2026-05-24 | Postgres schema, FastF1 ingest, Streamlit skeleton, cloud deploy | 6 | 0 | 0% | 5 | 0 | 0 | Future
4 | Phase 2 — Pipeline | 2026-05-25 | 2026-05-31 | Dashboard polish, README pass, v0.2 tag, LinkedIn #2 | 6 | 0 | 0% | 10 | 0 | 0 | Future
5 | Phase 3 — Predictor | 2026-06-01 | 2026-06-07 | Leakage tripwire FIRST, bicycle model, Brunel WhatsApp | 6 | 0 | 0% | 10 | 0 | 0 | Future
6 | Phase 3 — Predictor | 2026-06-08 | 2026-06-14 | Tire degradation curve, physics-model.md | 4 | 0 | 0% | 10 | 0 | 0 | Future
7 | Phase 3 — Predictor | 2026-06-15 | 2026-06-21 | Residual ML + conformal calibration, v0.3, LinkedIn #3 | 8 | 0 | 0% | 10 | 0 | 0 | Future
8 | Phase 4 — Counterfactual | 2026-06-22 | 2026-06-28 | Perturbation API, action vocabulary | 4 | 0 | 0% | 10 | 0 | 0 | Future
9 | Phase 4 — Counterfactual | 2026-06-29 | 2026-07-05 | What-if Streamlit page, screenshot for demo, LinkedIn #4 | 5 | 0 | 0% | 10 | 0 | 0 | Future
10 | Phase 5 — Always-on | 2026-07-06 | 2026-07-12 | Replay engine, Tier 1 + Tier 3 ticks, Watch feed | 4 | 0 | 0% | 10 | 0 | 0 | Future
11 | Phase 5 — Always-on | 2026-07-13 | 2026-07-19 | Monte Carlo slim layer, MATLAB port starts, v0.5, LinkedIn #5 | 5 | 0 | 0% | 10 | 0 | 0 | Future
12 | Phase 6 — LLM + MATLAB | 2026-07-20 | 2026-07-26 | Llama narrator, RAG-grounded Ask mode | 4 | 0 | 0% | 10 | 0 | 0 | Future
13 | Phase 6 — LLM + MATLAB | 2026-07-27 | 2026-08-02 | MATLAB port finish, LLM polish, v0.6, LinkedIn #6 | 5 | 0 | 0% | 8 | 0 | 0 | Future
14 | Phase 7 — Eval + demo | 2026-08-03 | 2026-08-09 | Eval pack, strategy backtest report, conformal coverage | 4 | 0 | 0% | 8 | 0 | 0 | Future
15 | Phase 7 — Eval + demo | 2026-08-10 | 2026-08-16 | Demo video, Replay mode, HF Space, v1.0, LinkedIn #7 | 7 | 0 | 0% | 8 | 0 | 0 | Future
16 | Phase 8 — App pack | 2026-08-17 | 2026-08-23 | CV rewrite, blog posts, cover letters, Careers review | 5 | 0 | 0% | 8 | 0 | 0 | Future
17 | Phase 8 — App pack | 2026-08-24 | 2026-08-31 | Alumni outreach, mock interviews, canonical questions | 5 | 0 | 0% | 8 | 0 | 0 | Future
18 | Phase 9 — Sustain | 2026-09-01 | 2026-09-07 | Apps open: fire first wave, weekly cadence locked | 0 | 0 | 0% | 5 | 0 | 0 | Future
19 | Phase 9 — Sustain | 2026-09-08 | 2026-09-14 | Apps wave 2, mock interviews #2-3, LeetCode-easy daily | 0 | 0 | 0% | 5 | 0 | 0 | Future
20 | Phase 9 — Sustain | 2026-09-15 | 2026-09-21 | Apps wave 3, sim-racing adapter starts (if time) | 0 | 0 | 0% | 5 | 0 | 0 | Future
21 | Phase 9 — Sustain | 2026-09-22 | 2026-09-28 | Follow-ups, mock interviews #4-5 | 0 | 0 | 0% | 5 | 0 | 0 | Future
22 | Phase 9 — Sustain | 2026-09-29 | 2026-10-05 | Apps wave 4, LinkedIn post (only if new artefact) | 0 | 0 | 0% | 5 | 0 | 0 | Future
Formulas:
Status = IF(TODAY()<[Start],"Future",IF(TODAY()>[End],IF([ARIS %]>=0.9,"Complete","Past Due"),"Current"))

## Daily Log
Date | Day | ARIS hrs | DSA hrs | App Tool hrs | Networking hrs | Writing hrs | Resources hrs | Other hrs | Total hrs | Target hrs | Vs Target | Notes
2026-04-29 | Wed | - | - | - | - | - | - | - | 0 | 6 | -6
2026-04-30 | Thu | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-01 | Fri | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-02 | Sat | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-03 | Sun | - | - | - | - | - | - | - | 0 | 0 | 0
2026-05-04 | Mon | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-05 | Tue | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-06 | Wed | - | - | - | - | - | - | - | 0 | 6 | -6
2026-05-07 | Thu | [7 empty] | 0 | 6 | -6
2026-05-08 | Fri | [7 empty] | 0 | 6 | -6
2026-05-09 | Sat | [7 empty] | 0 | 6 | -6
2026-05-10 | Sun | [7 empty] | 0 | 0 | 0
2026-05-11 | Mon | [7 empty] | 0 | 6 | -6
2026-05-12 | Tue | [7 empty] | 0 | 6 | -6
2026-05-13 | Wed | [7 empty] | 0 | 6 | -6
2026-05-14 | Thu | [7 empty] | 0 | 6 | -6
2026-05-15 | Fri | [7 empty] | 0 | 6 | -6
2026-05-16 | Sat | [7 empty] | 0 | 6 | -6
2026-05-17 | Sun | [7 empty] | 0 | 0 | 0
2026-05-18 | Mon | [7 empty] | 0 | 6 | -6
2026-05-19 | Tue | [7 empty] | 0 | 6 | -6
2026-05-20 | Wed | [7 empty] | 0 | 6 | -6
2026-05-21 | Thu | [7 empty] | 0 | 6 | -6
2026-05-22 | Fri | [7 empty] | 0 | 6 | -6
2026-05-23 | Sat | [7 empty] | 0 | 6 | -6
2026-05-24 | Sun | [7 empty] | 0 | 0 | 0
2026-05-25 | Mon | [7 empty] | 0 | 6 | -6
2026-05-26 | Tue | [7 empty] | 0 | 6 | -6
2026-05-27 | Wed | [7 empty] | 0 | 6 | -6
2026-05-28 | Thu | [7 empty] | 0 | 6 | -6
2026-05-29 | Fri | [7 empty] | 0 | 6 | -6
2026-05-30 | Sat | [7 empty] | 0 | 6 | -6
2026-05-31 | Sun | [7 empty] | 0 | 0 | 0
2026-06-01 | Mon | [7 empty] | 0 | 6 | -6
2026-06-02 | Tue | [7 empty] | 0 | 6 | -6
2026-06-03 | Wed | [7 empty] | 0 | 6 | -6
2026-06-04 | Thu | [7 empty] | 0 | 6 | -6
2026-06-05 | Fri | [7 empty] | 0 | 6 | -6
2026-06-06 | Sat | [7 empty] | 0 | 6 | -6
2026-06-07 | Sun | [7 empty] | 0 | 0 | 0
2026-06-08 | Mon | [7 empty] | 0 | 6 | -6
2026-06-09 | Tue | [7 empty] | 0 | 6 | -6
2026-06-10 | Wed | [7 empty] | 0 | 6 | -6
2026-06-11 | Thu | [7 empty] | 0 | 6 | -6
2026-06-12 | Fri | [7 empty] | 0 | 6 | -6
2026-06-13 | Sat | [7 empty] | 0 | 6 | -6
2026-06-14 | Sun | [7 empty] | 0 | 0 | 0
2026-06-15 | Mon | [7 empty] | 0 | 6 | -6
2026-06-16 | Tue | [7 empty] | 0 | 6 | -6
2026-06-17 | Wed | [7 empty] | 0 | 6 | -6
2026-06-18 | Thu | [7 empty] | 0 | 6 | -6
2026-06-19 | Fri | [7 empty] | 0 | 6 | -6
2026-06-20 | Sat | [7 empty] | 0 | 6 | -6
2026-06-21 | Sun | [7 empty] | 0 | 0 | 0
2026-06-22 | Mon | [7 empty] | 0 | 6 | -6
2026-06-23 | Tue | [7 empty] | 0 | 6 | -6
2026-06-24 | Wed | [7 empty] | 0 | 6 | -6
2026-06-25 | Thu | [7 empty] | 0 | 6 | -6
2026-06-26 | Fri | [7 empty] | 0 | 6 | -6
2026-06-27 | Sat | [7 empty] | 0 | 6 | -6
2026-06-28 | Sun | [7 empty] | 0 | 0 | 0
2026-06-29 | Mon | [7 empty] | 0 | 6 | -6
2026-06-30 | Tue | [7 empty] | 0 | 6 | -6
2026-07-01 | Wed | [7 empty] | 0 | 6 | -6
2026-07-02 | Thu | [7 empty] | 0 | 6 | -6
2026-07-03 | Fri | [7 empty] | 0 | 6 | -6
2026-07-04 | Sat | [7 empty] | 0 | 6 | -6
2026-07-05 | Sun | [7 empty] | 0 | 0 | 0
2026-07-06 | Mon | [7 empty] | 0 | 6 | -6
2026-07-07 | Tue | [7 empty] | 0 | 6 | -6
2026-07-08 | Wed | [7 empty] | 0 | 6 | -6
2026-07-09 | Thu | [7 empty] | 0 | 6 | -6
2026-07-10 | Fri | [7 empty] | 0 | 6 | -6
2026-07-11 | Sat | [7 empty] | 0 | 6 | -6
2026-07-12 | Sun | [7 empty] | 0 | 0 | 0
2026-07-13 | Mon | [7 empty] | 0 | 6 | -6
2026-07-14 | Tue | [7 empty] | 0 | 6 | -6
2026-07-15 | Wed | [7 empty] | 0 | 6 | -6
2026-07-16 | Thu | [7 empty] | 0 | 6 | -6
2026-07-17 | Fri | [7 empty] | 0 | 6 | -6
2026-07-18 | Sat | [7 empty] | 0 | 6 | -6
2026-07-19 | Sun | [7 empty] | 0 | 0 | 0
2026-07-20 | Mon | [7 empty] | 0 | 6 | -6
2026-07-21 | Tue | [7 empty] | 0 | 6 | -6
2026-07-22 | Wed | [7 empty] | 0 | 6 | -6
2026-07-23 | Thu | [7 empty] | 0 | 6 | -6
2026-07-24 | Fri | [7 empty] | 0 | 6 | -6
2026-07-25 | Sat | [7 empty] | 0 | 6 | -6
2026-07-26 | Sun | [7 empty] | 0 | 0 | 0
2026-07-27 | Mon | [7 empty] | 0 | 6 | -6
2026-07-28 | Tue | [7 empty] | 0 | 6 | -6
2026-07-29 | Wed | [7 empty] | 0 | 6 | -6
2026-07-30 | Thu | [7 empty] | 0 | 6 | -6
2026-07-31 | Fri | [7 empty] | 0 | 6 | -6
2026-08-01 | Sat | [7 empty] | 0 | 6 | -6
2026-08-02 | Sun | [7 empty] | 0 | 0 | 0
2026-08-03 | Mon | [7 empty] | 0 | 6 | -6
2026-08-04 | Tue | [7 empty] | 0 | 6 | -6
2026-08-05 | Wed | [7 empty] | 0 | 6 | -6
2026-08-06 | Thu | [7 empty] | 0 | 6 | -6
2026-08-07 | Fri | [7 empty] | 0 | 6 | -6
2026-08-08 | Sat | [7 empty] | 0 | 6 | -6
2026-08-09 | Sun | [7 empty] | 0 | 0 | 0
2026-08-10 | Mon | [7 empty] | 0 | 6 | -6
2026-08-11 | Tue | [7 empty] | 0 | 6 | -6
2026-08-12 | Wed | [7 empty] | 0 | 6 | -6
2026-08-13 | Thu | [7 empty] | 0 | 6 | -6
2026-08-14 | Fri | [7 empty] | 0 | 6 | -6
2026-08-15 | Sat | [7 empty] | 0 | 6 | -6
2026-08-16 | Sun | [7 empty] | 0 | 0 | 0
2026-08-17 | Mon | [7 empty] | 0 | 6 | -6
2026-08-18 | Tue | [7 empty] | 0 | 6 | -6
2026-08-19 | Wed | [7 empty] | 0 | 6 | -6
2026-08-20 | Thu | [7 empty] | 0 | 6 | -6
2026-08-21 | Fri | [7 empty] | 0 | 6 | -6
2026-08-22 | Sat | [7 empty] | 0 | 6 | -6
2026-08-23 | Sun | [7 empty] | 0 | 0 | 0
2026-08-24 | Mon | [7 empty] | 0 | 6 | -6
2026-08-25 | Tue | [7 empty] | 0 | 6 | -6
2026-08-26 | Wed | [7 empty] | 0 | 6 | -6
2026-08-27 | Thu | [7 empty] | 0 | 6 | -6
2026-08-28 | Fri | [7 empty] | 0 | 6 | -6
2026-08-29 | Sat | [7 empty] | 0 | 6 | -6
2026-08-30 | Sun | [7 empty] | 0 | 0 | 0
2026-08-31 | Mon | [7 empty] | 0 | 6 | -6
2026-09-01 | Tue | [7 empty] | 0 | 6 | -6
2026-09-02 | Wed | [7 empty] | 0 | 6 | -6
2026-09-03 | Thu | [7 empty] | 0 | 6 | -6
2026-09-04 | Fri | [7 empty] | 0 | 6 | -6
2026-09-05 | Sat | [7 empty] | 0 | 6 | -6
2026-09-06 | Sun | [7 empty] | 0 | 0 | 0
2026-09-07 | Mon | [7 empty] | 0 | 6 | -6
2026-09-08 | Tue | [7 empty] | 0 | 6 | -6
2026-09-09 | Wed | [7 empty] | 0 | 6 | -6
2026-09-10 | Thu | [7 empty] | 0 | 6 | -6
2026-09-11 | Fri | [7 empty] | 0 | 6 | -6
2026-09-12 | Sat | [7 empty] | 0 | 6 | -6
2026-09-13 | Sun | [7 empty] | 0 | 0 | 0
2026-09-14 | Mon | [7 empty] | 0 | 6 | -6
2026-09-15 | Tue | [7 empty] | 0 | 6 | -6
2026-09-16 | Wed | [7 empty] | 0 | 6 | -6
2026-09-17 | Thu | [7 empty] | 0 | 6 | -6
2026-09-18 | Fri | [7 empty] | 0 | 6 | -6
2026-09-19 | Sat | [7 empty] | 0 | 6 | -6
2026-09-20 | Sun | [7 empty] | 0 | 0 | 0
2026-09-21 | Mon | [7 empty] | 0 | 6 | -6
2026-09-22 | Tue | [7 empty] | 0 | 6 | -6
2026-09-23 | Wed | [7 empty] | 0 | 6 | -6
2026-09-24 | Thu | [7 empty] | 0 | 6 | -6
2026-09-25 | Fri | [7 empty] | 0 | 6 | -6
2026-09-26 | Sat | [7 empty] | 0 | 6 | -6
2026-09-27 | Sun | [7 empty] | 0 | 0 | 0
2026-09-28 | Mon | [7 empty] | 0 | 6 | -6
2026-09-29 | Tue | [7 empty] | 0 | 6 | -6
2026-09-30 | Wed | [7 empty] | 0 | 6 | -6
2026-10-01 | Thu | [7 empty] | 0 | 6 | -6
2026-10-02 | Fri | [7 empty] | 0 | 6 | -6
2026-10-03 | Sat | [7 empty] | 0 | 6 | -6
2026-10-04 | Sun | [7 empty] | 0 | 0 | 0
2026-10-05 | Mon | [7 empty] | 0 | 6 | -6
2026-10-06 | Tue | [7 empty] | 0 | 6 | -6
2026-10-07 | Wed | [7 empty] | 0 | 6 | -6
2026-10-08 | Thu | [7 empty] | 0 | 6 | -6
2026-10-09 | Fri | [7 empty] | 0 | 6 | -6
2026-10-10 | Sat | [7 empty] | 0 | 6 | -6
2026-10-11 | Sun | [7 empty] | 0 | 0 | 0
2026-10-12 | Mon | [7 empty] | 0 | 6 | -6
2026-10-13 | Tue | [7 empty] | 0 | 6 | -6
2026-10-14 | Wed | [7 empty] | 0 | 6 | -6
2026-10-15 | Thu | [7 empty] | 0 | 6 | -6
2026-10-16 | Fri | [7 empty] | 0 | 6 | -6
2026-10-17 | Sat | [7 empty] | 0 | 6 | -6
2026-10-18 | Sun | [7 empty] | 0 | 0 | 0
2026-10-19 | Mon | [7 empty] | 0 | 6 | -6
2026-10-20 | Tue | [7 empty] | 0 | 6 | -6
2026-10-21 | Wed | [7 empty] | 0 | 6 | -6
2026-10-22 | Thu | [7 empty] | 0 | 6 | -6
2026-10-23 | Fri | [7 empty] | 0 | 6 | -6
2026-10-24 | Sat | [7 empty] | 0 | 6 | -6
2026-10-25 | Sun | [7 empty] | 0 | 0 | 0
2026-10-26 | Mon | [7 empty] | 0 | 6 | -6
2026-10-27 | Tue | [7 empty] | 0 | 6 | -6
2026-10-28 | Wed | [7 empty] | 0 | 6 | -6
2026-10-29 | Thu | [7 empty] | 0 | 6 | -6
2026-10-30 | Fri | [7 empty] | 0 | 6 | -6
2026-10-31 | Sat | [7 empty] | 0 | 6 | -6
2026-11-01 | Sun | [7 empty] | 0 | 0 | 0
2026-11-02 | Mon | [7 empty] | 0 | 6 | -6
2026-11-03 | Tue | [7 empty] | 0 | 6 | -6
2026-11-04 | Wed | [7 empty] | 0 | 6 | -6
2026-11-05 | Thu | [7 empty] | 0 | 6 | -6
2026-11-06 | Fri | [7 empty] | 0 | 6 | -6
2026-11-07 | Sat | [7 empty] | 0 | 6 | -6
2026-11-08 | Sun | [7 empty] | 0 | 0 | 0
2026-11-09 | Mon | [7 empty] | 0 | 6 | -6
2026-11-10 | Tue | [7 empty] | 0 | 6 | -6
2026-11-11 | Wed | [7 empty] | 0 | 6 | -6
2026-11-12 | Thu | [7 empty] | 0 | 6 | -6
2026-11-13 | Fri | [7 empty] | 0 | 6 | -6
2026-11-14 | Sat | [7 empty] | 0 | 6 | -6

## ARIS Tasks
Phase | Week | Task | Tier | Status | Hours Est | Hours Actual | Date Done | Notes
Phase 0 | 0 | Install Python 3.11.9 via pyenv-win; verify version | Core | Done | 1 | 1
Phase 0 | 0 | Install uv; verify uv --version | Core | Done | 0.5 | 0.5
Phase 0 | 0 | Install Git for Windows + GitHub CLI; gh auth login | Core | Done | 1 | 0.5
Phase 0 | 0 | Install VS Code + extensions (Python, Pylance, Ruff, Jupyter, Docker, GitLens, Mermaid, Markdown) | Core | Done | 1 | 0.5
Phase 0 | 0 | Install Docker Desktop; docker run hello-world works | Core | Todo | 1
Phase 0 | 0 | Install latest NVIDIA driver; nvidia-smi shows RTX 5070 | Core | Done | 0.5 | 0.5
Phase 0 | 0 | Install CUDA Toolkit 12.x; nvcc --version works | Core | Done | 1 | 0.5
Phase 0 | 0 | Install Ollama; ollama --version works | Core | Done | 0.5 | 1
Phase 0 | 0 | ollama pull llama3.1:8b-instruct-q5_K_M and verify GPU prompt | Core | Todo | 1 | 0
Phase 0 | 0 | ollama pull llama3.2:3b (fallback) | Tier C | Todo | 0.5 | 0
Phase 0 | 0 | Install DBeaver Community | Tier C | Done | 0.5 | 0.2
Phase 0 | 0 | Install OBS Studio + DaVinci Resolve / CapCut | Core | Done | 1 | 0.2
Phase 0 | 0 | Set up MATLAB Online or Brunel R2024b student license | Tier B | Todo | 1 | 0
Phase 0 | 0 | Set up Obsidian vault for personal notes (outside repo) | Core | Todo | 0.5 | 0
Phase 0 | 0 | Create accounts: Streamlit Cloud, Neon.tech, HF, MathWorks, Coursera, DLAI, Bright Network | Core | Todo | 1 | 0
Phase 0 | 0 | Clean GitHub: purge NeuroSim, write ARIS-aligned README, pin repos | Tier A | Todo | 2 | 0
Phase 0 | 0 | Create empty aris repo (public, MIT, gitignore) | Core | Done | 0.5 | 0
Phase 0 | 0 | Reserve Rajamani + Milliken from Brunel library | Core | Todo | 0.5 | 0
Phase 0 | 0 | Identify Brunel Racing contact (name + role) | Tier A | Todo | 1 | 0
Phase 0 | 0 | Book Brunel Careers Service 1:1 for May | Core | Todo | 0.5 | 0
Phase 0 | 0 | Flag a friend now for mock interviews in Week 16 | Core | Doing | 0.25 | 0
Phase 1 | 1 | Initial commit to aris (README, pyproject.toml via uv init, gitignore, MIT) | Core | Todo | 1 | 0
Phase 1 | 1 | Boot.dev Python track through OOP basics | Core | Todo | 8 | 0
Phase 1 | 1 | NumPy basics — arrays, slicing, broadcasting | Core | Todo | 4 | 0
Phase 1 | 1 | First daily commit streak (≥1 commit every weekday) | Core | Todo | 1 | 0
Phase 1 | 1 | LOG.md created; daily two-line journal entries | Core | Todo | 0.5 | 0
Phase 1 | 1 | LinkedIn post #1 — starting ARIS (announcement) | Tier A | Todo | 1 | 0
Phase 1 | 2 | Finish Boot.dev OOP / numpy module | Core | Todo | 6 | 0
Phase 1 | 2 | James Powell pandas tutorials (2 hrs YouTube) | Core | Todo | 2 | 0
Phase 1 | 2 | uv add fastf1 matplotlib pandas jupyterlab | Core | Todo | 0.5 | 0
Phase 1 | 2 | Pull one race via FastF1 (e.g. 2023 Bahrain GP) | Core | Todo | 2 | 0
Phase 1 | 2 | Plot one driver lap times in matplotlib; commit chart + notebook | Core | Todo | 3 | 0
Phase 1 | 2 | Statistical baseline — moving-avg sector times scoring stub on dummy data | Tier B | Todo | 4 | 0
Phase 1 | 2 | Push to main; tag v0.1-foundation | Core | Todo | 0.5 | 0
Phase 2 | 3 | Postgres 16 in Docker, schema for sessions/drivers/laps/telemetry | Core | Todo | 6 | 0
Phase 2 | 3 | FastF1 ingest script — idempotent re-runs | Core | Todo | 6 | 0
Phase 2 | 3 | Ingest 1 full season as test corpus | Core | Todo | 4 | 0
Phase 2 | 3 | Streamlit skeleton: pick driver/race, list lap times | Core | Todo | 4 | 0
Phase 2 | 3 | Cloud deploy (moved up from Wk4): push to Streamlit Community Cloud, get public URL | Tier A | Todo | 4 | 0
Phase 2 | 3 | Brunel Racing kill checkpoint (Day 5): commit pivot to LOG.md if no path | Tier A | Todo | 0.5 | 0
Phase 2 | 4 | Sector breakdown chart on Streamlit page | Core | Todo | 4 | 0
Phase 2 | 4 | Race selector with proper season/round dropdowns | Core | Todo | 3 | 0
Phase 2 | 4 | First README pass: live URL, screenshots, project pitch | Core | Todo | 4 | 0
Phase 2 | 4 | Tag v0.2-pipeline | Core | Todo | 0.5 | 0
Phase 2 | 4 | LinkedIn post #2 — first 3 weeks shipped (with public URL) | Tier A | Todo | 1 | 0
Phase 2 | 4 | Reclaimed week buffer: Phase 3 leakage debug or schema migrations | Core | Todo | 8 | 0
Phase 3 | 5 | Day 1 commit: tests/test_no_leakage.py — race-by-race CV harness + leakage unit test (Tier B graft, MOST IMPORTANT) | Tier B | Todo | 6 | 0
Phase 3 | 5 | Read Rajamani Ch. 2 (single-track bicycle model) | Core | Todo | 4 | 0
Phase 3 | 5 | Hand-code bicycle model in Python; plot predicted vs actual on one stint | Core | Todo | 8 | 0
Phase 3 | 5 | Add fuel-burn linear term + pit-loss constant | Tier B | Todo | 4 | 0
Phase 3 | 5 | Commit physics module with invariant tests (mass conservation, monotonic fuel burn) | Core | Todo | 3 | 0
Phase 3 | 5 | Send Brunel Racing WhatsApp (with live URL + chart attached) | Tier A | Todo | 0.5 | 0
Phase 3 | 6 | Tire degradation curve: linear-with-fuel + exponential wear (Pacejka-style simplified) | Core | Todo | 8 | 0
Phase 3 | 6 | Plug into physics model; re-plot stint | Core | Todo | 4 | 0
Phase 3 | 6 | Notebook: per-compound deg curves on real FastF1 stints | Core | Todo | 4 | 0
Phase 3 | 6 | Document assumptions in docs/physics-model.md | Core | Todo | 4 | 0
Phase 3 | 7 | Residual layer: XGBoost (or tiny sklearn MLP), target = (actual − physics) | Core | Todo | 8 | 0
Phase 3 | 7 | Train/test split BY RACE never by lap (leakage tripwire green) | Tier A | Todo | 2 | 0
Phase 3 | 7 | Compute MAE per fold; report against floor/target/stretch | Core | Todo | 4 | 0
Phase 3 | 7 | Split-conformal calibration harness — empirical coverage, per-stint width plot | Tier B | Todo | 6 | 0
Phase 3 | 7 | Strategy backtest stub (undercut/SC scaffolding) | Core | Todo | 3 | 0
Phase 3 | 7 | Brunel Racing kill checkpoint (Wk7 end): commit pivot if no reply | Tier A | Todo | 0.5 | 0
Phase 3 | 7 | Tag v0.3-predictor | Core | Todo | 0.5 | 0
Phase 3 | 7 | LinkedIn post #3 — first real result (MAE + conformal coverage chart) | Tier A | Todo | 1 | 0
Phase 4 | 8 | Action vocabulary: lift point, brake point, line offset, pit lap, compound choice | Core | Todo | 4 | 0
Phase 4 | 8 | simulate(state, action_change) returns delta + new predicted stint | Core | Todo | 8 | 0
Phase 4 | 8 | Property tests: monotonicity, idempotence on null action | Core | Todo | 4 | 0
Phase 4 | 8 | Hook into Phase 3 predictor | Core | Todo | 4 | 0
Phase 4 | 9 | What-if mode in Streamlit: real lap selector + action sliders | Core | Todo | 6 | 0
Phase 4 | 9 | Predicted delta + chart + before/after comparison | Core | Todo | 6 | 0
Phase 4 | 9 | Capture screenshot for demo video | Tier A | Todo | 1 | 0
Phase 4 | 9 | Tag v0.4-counterfactual | Core | Todo | 0.5 | 0
Phase 4 | 9 | LinkedIn post #4 — what-if simulator (lift 30m T7 → +0.18s screenshot) | Tier A | Todo | 1 | 0
Phase 5 | 10 | Replay engine: feed FastF1 historical lap-by-lap as if live | Core | Todo | 8 | 0
Phase 5 | 10 | Tier 1 monitor (every 1–2s): anomaly detection on telemetry | Core | Todo | 6 | 0
Phase 5 | 10 | Tier 3 macro (per lap): action search across pit/compound/defend/attack | Core | Todo | 6 | 0
Phase 5 | 10 | Streamlit Watch feed: scrolling cards, top-3 recommendations | Core | Todo | 6 | 0
Phase 5 | 11 | 3-day Monte Carlo slim layer: sample N continuations, win-prob delta | Core | Todo | 8 | 0
Phase 5 | 11 | Event-driven recompute hook (<400ms): SC/VSC, competitor pit, weather, pace | Core | Todo | 6 | 0
Phase 5 | 11 | MATLAB/Simulink port (evenings parallel): start aris-matlab-validation repo, bicycle module | Tier B | Todo | 6 | 0
Phase 5 | 11 | Tag v0.5-always-on | Core | Todo | 0.5 | 0
Phase 5 | 11 | LinkedIn post #5 — always-on loop (recommendation feed clip + tiered tick paragraph) | Tier A | Todo | 1 | 0
Phase 6 | 12 | Prompt template: structured JSON recommendation → human sentence | Core | Todo | 6 | 0
Phase 6 | 12 | Local Llama 3.1 8B narrating in real time during replay | Core | Todo | 8 | 0
Phase 6 | 12 | Ask mode: NL Q&A grounded in ARIS state (RAG over fits, residuals, MC runs) | Core | Todo | 8 | 0
Phase 6 | 12 | Citation in every answer (which fit/residual/MC run) | Core | Todo | 4 | 0
Phase 6 | 13 | Finish aris-matlab-validation: Simulink block diagram, comparison plot, README with placement framing | Tier B | Todo | 8 | 0
Phase 6 | 13 | Pin MATLAB repo on GitHub profile | Tier A | Todo | 0.25 | 0
Phase 6 | 13 | LLM prompt regression tests (sample inputs → expected sentence shapes) | Core | Todo | 6 | 0
Phase 6 | 13 | Tag v0.6-narrated | Core | Todo | 0.5 | 0
Phase 6 | 13 | LinkedIn post #6 — narrated strategy + MATLAB validation (two signals one post) | Tier A | Todo | 1 | 0
Phase 7 | 14 | Backtest on 5 held-out races; full eval table | Core | Todo | 10 | 0
Phase 7 | 14 | Conformal calibration empirical coverage check; coverage curve plot | Tier B | Todo | 6 | 0
Phase 7 | 14 | docs/strategy-backtest.md — undercut risk, SC sensitivity, pit-window deltas, hit-rate | Tier A | Todo | 8 | 0
Phase 7 | 14 | Phase 7 kill criterion check: if demo > 5 days, ship 60-second cut | Tier A | Todo | 0.5 | 0
Phase 7 | 15 | Replay mode: scrub past laps, ARIS would-have vs actually-did | Core | Todo | 6 | 0
Phase 7 | 15 | OBS screen recording — three beats (live watching, lap 23 recommend, validation summary) | Core | Todo | 8 | 0
Phase 7 | 15 | Edit in DaVinci/CapCut; final cut ≤ 90s; voiceover (Claude API for polish) | Core | Todo | 8 | 0
Phase 7 | 15 | Upload to YouTube unlisted; embed in main README | Core | Todo | 1 | 0
Phase 7 | 15 | Hugging Face Space (Tier C): deploy ARIS Watch mode publicly | Tier C | Todo | 4 | 0
Phase 7 | 15 | Tag v1.0-shipped | Core | Todo | 0.5 | 0
Phase 7 | 15 | LinkedIn post #7 — ARIS shipped (flagship: pin demo, repo, HF Space, backtest) | Tier A | Todo | 1 | 0
Phase 8 | 16 | CV rewrite: ARIS at top, mapped to role-language table | Tier A | Todo | 8 | 0
Phase 8 | 16 | Brunel Careers Service review on new CV | Core | Todo | 1 | 0
Phase 8 | 16 | LinkedIn post #8 — technical deep-dive long-form (cross-post Medium) | Tier A | Todo | 6 | 0
Phase 8 | 16 | LinkedIn post #9 — motivation/story long-form (cross-post Medium) | Tier A | Todo | 4 | 0
Phase 8 | 16 | Cover-letter templates per team (Williams, McLaren, RB, Mercedes HPP, Aston Martin, M-Sport, Alpine, AP Racing, Bentley) | Tier A | Todo | 8 | 0
Phase 8 | 17 | 3 cold messages/week to Brunel alumni at target firms | Tier A | Todo | 4 | 0
Phase 8 | 17 | Mock interview #1 with Week 0 friend | Core | Todo | 2 | 0
Phase 8 | 17 | Drill 5 canonical strategy questions (undercut/overcut, gap-to-leader, 1v2-stop, pit-stop walk, defend-decision) | Core | Todo | 6 | 0
Phase 8 | 17 | Walk-through dry-run: open any line of ARIS, answer 5-question test | Core | Todo | 4 | 0
Phase 8 | 17 | Final tag v1.0-placement-ready; freeze main | Core | Todo | 0.5 | 0

## DSA Tracker
# | Problem | Pattern | Difficulty | Status | Date Solved | Time (min) | Source | Notes
1 | Contains Duplicate | Arrays & Hashing | Easy | Todo |  |  | NeetCode 150
2 | Valid Anagram | Arrays & Hashing | Easy | Todo |  |  | NeetCode 150
3 | Two Sum | Arrays & Hashing | Easy | Todo |  |  | NeetCode 150
4 | Group Anagrams | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
5 | Top K Frequent Elements | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
6 | Encode and Decode Strings | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
7 | Product of Array Except Self | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
8 | Valid Sudoku | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
9 | Longest Consecutive Sequence | Arrays & Hashing | Medium | Todo |  |  | NeetCode 150
10 | Valid Palindrome | Two Pointers | Easy | Todo |  |  | NeetCode 150
11 | Two Sum II - Input Array Is Sorted | Two Pointers | Medium | Todo |  |  | NeetCode 150
12 | 3Sum | Two Pointers | Medium | Todo |  |  | NeetCode 150
13 | Container With Most Water | Two Pointers | Medium | Todo |  |  | NeetCode 150
14 | Trapping Rain Water | Two Pointers | Hard | Todo |  |  | NeetCode 150
15 | Best Time to Buy and Sell Stock | Sliding Window | Easy | Todo |  |  | NeetCode 150
16 | Longest Substring Without Repeating Characters | Sliding Window | Medium | Todo |  |  | NeetCode 150
17 | Longest Repeating Character Replacement | Sliding Window | Medium | Todo |  |  | NeetCode 150
18 | Permutation in String | Sliding Window | Medium | Todo |  |  | NeetCode 150
19 | Minimum Window Substring | Sliding Window | Hard | Todo |  |  | NeetCode 150
20 | Sliding Window Maximum | Sliding Window | Hard | Todo |  |  | NeetCode 150
21 | Valid Parentheses | Stack | Easy | Todo |  |  | NeetCode 150
22 | Min Stack | Stack | Medium | Todo |  |  | NeetCode 150
23 | Evaluate Reverse Polish Notation | Stack | Medium | Todo |  |  | NeetCode 150
24 | Generate Parentheses | Stack | Medium | Todo |  |  | NeetCode 150
25 | Daily Temperatures | Stack | Medium | Todo |  |  | NeetCode 150
26 | Car Fleet | Stack | Medium | Todo |  |  | NeetCode 150
27 | Largest Rectangle in Histogram | Stack | Hard | Todo |  |  | NeetCode 150
28 | Binary Search | Binary Search | Easy | Todo |  |  | NeetCode 150
29 | Search a 2D Matrix | Binary Search | Medium | Todo |  |  | NeetCode 150
30 | Koko Eating Bananas | Binary Search | Medium | Todo |  |  | NeetCode 150
31 | Find Minimum in Rotated Sorted Array | Binary Search | Medium | Todo |  |  | NeetCode 150
32 | Search in Rotated Sorted Array | Binary Search | Medium | Todo |  |  | NeetCode 150
33 | Time Based Key-Value Store | Binary Search | Medium | Todo |  |  | NeetCode 150
34 | Median of Two Sorted Arrays | Binary Search | Hard | Todo |  |  | NeetCode 150
35 | Reverse Linked List | Linked List | Easy | Todo |  |  | NeetCode 150
36 | Merge Two Sorted Lists | Linked List | Easy | Todo |  |  | NeetCode 150
37 | Reorder List | Linked List | Medium | Todo |  |  | NeetCode 150
38 | Remove Nth Node From End of List | Linked List | Medium | Todo |  |  | NeetCode 150
39 | Copy List with Random Pointer | Linked List | Medium | Todo |  |  | NeetCode 150
40 | Add Two Numbers | Linked List | Medium | Todo |  |  | NeetCode 150
41 | Linked List Cycle | Linked List | Easy | Todo |  |  | NeetCode 150
42 | Find the Duplicate Number | Linked List | Medium | Todo |  |  | NeetCode 150
43 | LRU Cache | Linked List | Medium | Todo |  |  | NeetCode 150
44 | Merge K Sorted Lists | Linked List | Hard | Todo |  |  | NeetCode 150
45 | Reverse Nodes in K-Group | Linked List | Hard | Todo |  |  | NeetCode 150
46 | Invert Binary Tree | Trees | Easy | Todo |  |  | NeetCode 150
47 | Maximum Depth of Binary Tree | Trees | Easy | Todo |  |  | NeetCode 150
48 | Diameter of Binary Tree | Trees | Easy | Todo |  |  | NeetCode 150
49 | Balanced Binary Tree | Trees | Easy | Todo |  |  | NeetCode 150
50 | Same Tree | Trees | Easy | Todo |  |  | NeetCode 150
51 | Subtree of Another Tree | Trees | Easy | Todo |  |  | NeetCode 150
52 | Lowest Common Ancestor of a BST | Trees | Medium | Todo |  |  | NeetCode 150
53 | Binary Tree Level Order Traversal | Trees | Medium | Todo |  |  | NeetCode 150
54 | Binary Tree Right Side View | Trees | Medium | Todo |  |  | NeetCode 150
55 | Count Good Nodes In Binary Tree | Trees | Medium | Todo |  |  | NeetCode 150
56 | Validate Binary Search Tree | Trees | Medium | Todo |  |  | NeetCode 150
57 | Kth Smallest Element in a BST | Trees | Medium | Todo |  |  | NeetCode 150
58 | Construct Binary Tree from Preorder and Inorder Traversal | Trees | Medium | Todo |  |  | NeetCode 150
59 | Binary Tree Maximum Path Sum | Trees | Hard | Todo |  |  | NeetCode 150
60 | Serialize and Deserialize Binary Tree | Trees | Hard | Todo |  |  | NeetCode 150
61 | Implement Trie (Prefix Tree) | Tries | Medium | Todo |  |  | NeetCode 150
62 | Design Add and Search Words Data Structure | Tries | Medium | Todo |  |  | NeetCode 150
63 | Word Search II | Tries | Hard | Todo |  |  | NeetCode 150
64 | Kth Largest Element in a Stream | Heap | Easy | Todo |  |  | NeetCode 150
65 | Last Stone Weight | Heap | Easy | Todo |  |  | NeetCode 150
66 | K Closest Points to Origin | Heap | Medium | Todo |  |  | NeetCode 150
67 | Kth Largest Element in an Array | Heap | Medium | Todo |  |  | NeetCode 150
68 | Task Scheduler | Heap | Medium | Todo |  |  | NeetCode 150
69 | Design Twitter | Heap | Medium | Todo |  |  | NeetCode 150
70 | Find Median from Data Stream | Heap | Hard | Todo |  |  | NeetCode 150
71 | Subsets | Backtracking | Medium | Todo |  |  | NeetCode 150
72 | Combination Sum | Backtracking | Medium | Todo |  |  | NeetCode 150
73 | Permutations | Backtracking | Medium | Todo |  |  | NeetCode 150
74 | Subsets II | Backtracking | Medium | Todo |  |  | NeetCode 150
75 | Combination Sum II | Backtracking | Medium | Todo |  |  | NeetCode 150
76 | Word Search | Backtracking | Medium | Todo |  |  | NeetCode 150
77 | Palindrome Partitioning | Backtracking | Medium | Todo |  |  | NeetCode 150
78 | Letter Combinations of a Phone Number | Backtracking | Medium | Todo |  |  | NeetCode 150
79 | N-Queens | Backtracking | Hard | Todo |  |  | NeetCode 150
80 | Number of Islands | Graphs | Medium | Todo |  |  | NeetCode 150
81 | Max Area of Island | Graphs | Medium | Todo |  |  | NeetCode 150
82 | Clone Graph | Graphs | Medium | Todo |  |  | NeetCode 150
83 | Walls and Gates | Graphs | Medium | Todo |  |  | NeetCode 150
84 | Rotting Oranges | Graphs | Medium | Todo |  |  | NeetCode 150
85 | Pacific Atlantic Water Flow | Graphs | Medium | Todo |  |  | NeetCode 150
86 | Surrounded Regions | Graphs | Medium | Todo |  |  | NeetCode 150
87 | Course Schedule | Graphs | Medium | Todo |  |  | NeetCode 150
88 | Course Schedule II | Graphs | Medium | Todo |  |  | NeetCode 150
89 | Graph Valid Tree | Graphs | Medium | Todo |  |  | NeetCode 150
90 | Number of Connected Components in an Undirected Graph | Graphs | Medium | Todo |  |  | NeetCode 150
91 | Redundant Connection | Graphs | Medium | Todo |  |  | NeetCode 150
92 | Word Ladder | Graphs | Hard | Todo |  |  | NeetCode 150
93 | Reconstruct Itinerary | Advanced Graphs | Hard | Todo |  |  | NeetCode 150
94 | Min Cost to Connect All Points | Advanced Graphs | Medium | Todo |  |  | NeetCode 150
95 | Network Delay Time | Advanced Graphs | Medium | Todo |  |  | NeetCode 150
96 | Swim in Rising Water | Advanced Graphs | Hard | Todo |  |  | NeetCode 150
97 | Alien Dictionary | Advanced Graphs | Hard | Todo |  |  | NeetCode 150
98 | Cheapest Flights Within K Stops | Advanced Graphs | Medium | Todo |  |  | NeetCode 150
99 | Climbing Stairs | 1-D DP | Easy | Todo |  |  | NeetCode 150
100 | Min Cost Climbing Stairs | 1-D DP | Easy | Todo |  |  | NeetCode 150
101 | House Robber | 1-D DP | Medium | Todo |  |  | NeetCode 150
102 | House Robber II | 1-D DP | Medium | Todo |  |  | NeetCode 150
103 | Longest Palindromic Substring | 1-D DP | Medium | Todo |  |  | NeetCode 150
104 | Palindromic Substrings | 1-D DP | Medium | Todo |  |  | NeetCode 150
105 | Decode Ways | 1-D DP | Medium | Todo |  |  | NeetCode 150
106 | Coin Change | 1-D DP | Medium | Todo |  |  | NeetCode 150
107 | Maximum Product Subarray | 1-D DP | Medium | Todo |  |  | NeetCode 150
108 | Word Break | 1-D DP | Medium | Todo |  |  | NeetCode 150
109 | Longest Increasing Subsequence | 1-D DP | Medium | Todo |  |  | NeetCode 150
110 | Partition Equal Subset Sum | 1-D DP | Medium | Todo |  |  | NeetCode 150
111 | Unique Paths | 2-D DP | Medium | Todo |  |  | NeetCode 150
112 | Longest Common Subsequence | 2-D DP | Medium | Todo |  |  | NeetCode 150
113 | Best Time to Buy and Sell Stock with Cooldown | 2-D DP | Medium | Todo |  |  | NeetCode 150
114 | Coin Change II | 2-D DP | Medium | Todo |  |  | NeetCode 150
115 | Target Sum | 2-D DP | Medium | Todo |  |  | NeetCode 150
116 | Interleaving String | 2-D DP | Medium | Todo |  |  | NeetCode 150
117 | Longest Increasing Path in a Matrix | 2-D DP | Hard | Todo |  |  | NeetCode 150
118 | Distinct Subsequences | 2-D DP | Hard | Todo |  |  | NeetCode 150
119 | Edit Distance | 2-D DP | Hard | Todo |  |  | NeetCode 150
120 | Burst Balloons | 2-D DP | Hard | Todo |  |  | NeetCode 150
121 | Regular Expression Matching | 2-D DP | Hard | Todo |  |  | NeetCode 150
122 | Maximum Subarray | Greedy | Medium | Todo |  |  | NeetCode 150
123 | Jump Game | Greedy | Medium | Todo |  |  | NeetCode 150
124 | Jump Game II | Greedy | Medium | Todo |  |  | NeetCode 150
125 | Gas Station | Greedy | Medium | Todo |  |  | NeetCode 150
126 | Hand of Straights | Greedy | Medium | Todo |  |  | NeetCode 150
127 | Merge Triplets to Form Target Triplet | Greedy | Medium | Todo |  |  | NeetCode 150
128 | Partition Labels | Greedy | Medium | Todo |  |  | NeetCode 150
129 | Valid Parenthesis String | Greedy | Medium | Todo |  |  | NeetCode 150
130 | Insert Interval | Intervals | Medium | Todo |  |  | NeetCode 150
131 | Merge Intervals | Intervals | Medium | Todo |  |  | NeetCode 150
132 | Non-overlapping Intervals | Intervals | Medium | Todo |  |  | NeetCode 150
133 | Meeting Rooms | Intervals | Easy | Todo |  |  | NeetCode 150
134 | Meeting Rooms II | Intervals | Medium | Todo |  |  | NeetCode 150
135 | Minimum Interval to Include Each Query | Intervals | Hard | Todo |  |  | NeetCode 150
136 | Rotate Image | Math & Geometry | Medium | Todo |  |  | NeetCode 150
137 | Spiral Matrix | Math & Geometry | Medium | Todo |  |  | NeetCode 150
138 | Set Matrix Zeroes | Math & Geometry | Medium | Todo |  |  | NeetCode 150
139 | Happy Number | Math & Geometry | Easy | Todo |  |  | NeetCode 150
140 | Plus One | Math & Geometry | Easy | Todo |  |  | NeetCode 150
141 | Pow(x, n) | Math & Geometry | Medium | Todo |  |  | NeetCode 150
142 | Multiply Strings | Math & Geometry | Medium | Todo |  |  | NeetCode 150
143 | Detect Squares | Math & Geometry | Medium | Todo |  |  | NeetCode 150
144 | Single Number | Bit Manipulation | Easy | Todo |  |  | NeetCode 150
145 | Number of 1 Bits | Bit Manipulation | Easy | Todo |  |  | NeetCode 150
146 | Counting Bits | Bit Manipulation | Easy | Todo |  |  | NeetCode 150
147 | Reverse Bits | Bit Manipulation | Easy | Todo |  |  | NeetCode 150
148 | Missing Number | Bit Manipulation | Easy | Todo |  |  | NeetCode 150
149 | Sum of Two Integers | Bit Manipulation | Medium | Todo |  |  | NeetCode 150
150 | Reverse Integer | Bit Manipulation | Medium | Todo |  |  | NeetCode 150

## Resources
When | Domain | Resource | Type | Tier | Free? | URL/Source | Hours Est | Hours Done | Status | Verify Done When | Notes
Wk0-2 | Python | Boot.dev — Python track + OOP | Course | Primary | Paid | boot.dev | 30 | 0 | Todo | Completed Python + OOP modules; all exercises green
Wk0-2 | Python | Real Python tutorials + Mosh Hamedani Python (YouTube) | Course | Backup | Free | youtube.com/c/programmingwithmosh | 25 | 0 | Todo | Completed beginner + intermediate Python videos; can write a class confidently
Wk1-2 | Python | James Powell pandas tutorial (YouTube, ~2h) | Course | Primary | Free | youtube.com — search 'James Powell pandas' | 2 | 0 | Todo | Watched + replicated key examples in a Jupyter notebook
Wk1-2 | Python | Kaggle Pandas micro-course | Course | Backup | Free | kaggle.com/learn/pandas | 4 | 0 | Todo | All 6 exercises passed
Wk1-2 | Python | Fluent Python (Ramalho) — Ch.1-3 | Book | Primary | Library | Brunel library / O'Reilly | 6 | 0 | Todo | Read first 3 chapters; can explain duck typing + special methods
Wk1-2 | Python | Effective Python (Slatkin) — items 1-30 | Book | Backup | Library | Brunel library / O'Reilly | 5 | 0 | Todo | Read items 1-30; applied 5 patterns to ARIS code
Wk2-4 | ML | Andrew Ng — Machine Learning Specialization (Coursera) | Course | Primary | Free (audit) | coursera.org/specializations/machine-learning-introduction | 40 | 0 | Todo | Course 1 + Course 2 audited; certificates only if paid
Wk2-4 | ML | fast.ai Practical Deep Learning Part 1 | Course | Backup | Free | course.fast.ai | 40 | 0 | Todo | Lessons 1-4 watched + first notebook adapted to a personal dataset
Wk2-5 | ML | StatQuest with Josh Starmer — XGBoost, Gradient Boosting, Conformal Pred | Video series | Primary | Free | youtube.com/@statquest | 8 | 0 | Todo | Watched all relevant playlists; can sketch each algorithm on paper
Wk2-5 | ML | 3Blue1Brown — Neural Networks playlist | Video series | Backup | Free | youtube.com/@3blue1brown | 3 | 0 | Todo | Watched all 4 videos in NN series
Wk2-5 | ML | Hundred-Page ML Book (Burkov) | Book | Primary | Free PDF | themlbook.com — 'read first' draft chapters free | 8 | 0 | Todo | Read cover to cover; can explain bias/variance + cross-validation
Wk2-5 | ML | Designing Machine Learning Systems (Huyen) — Ch.4-6 | Book | Backup | Library | Brunel library / O'Reilly | 6 | 0 | Todo | Read chapters 4-6 (training data, feature eng, model dev)
Wk4-5 | Vehicle Dyn. | Rajamani — Vehicle Dynamics and Control, Ch.1-3 | Book | Primary | Library | Brunel library (reserve Wk0) | 8 | 0 | Todo | Can derive bicycle model on whiteboard from memory in <10 min
Wk4-5 | Vehicle Dyn. | MIT OCW 2.04A Systems & Controls — relevant lectures | Course | Backup | Free | ocw.mit.edu — search 2.04A | 6 | 0 | Todo | Watched lateral dynamics + tire model lectures
Wk4-5 | Vehicle Dyn. | Milliken — Race Car Vehicle Dynamics — reference | Book | Primary | Library | Brunel library | 4 | 0 | Todo | Skimmed Ch. 1 + 5 + 14 (tire mechanics)
Wk4-6 | Vehicle Dyn. | TUMFTM racesim_basic — read source code | Code | Primary | Free | github.com/TUMFTM/racesim | 6 | 0 | Todo | Read ingest + sim core; understood how stints are simulated
Wk6-7 | Stats/ML | Angelopoulos & Bates — Gentle Intro to Conformal Prediction | Paper | Primary | Free | arxiv.org/abs/2107.07511 | 4 | 0 | Todo | Read sections 1-3; implemented split-conformal on a toy regression
Wk6-7 | Stats/ML | MAPIE library + tutorials | Code | Backup | Free | github.com/scikit-learn-contrib/MAPIE | 3 | 0 | Todo | Ran MAPIE tutorial notebook end-to-end
Wk6-7 | Stats/ML | Forecasting: Principles and Practice (Hyndman) — Ch. 1-3, 5 | Book | Primary | Free | otexts.com/fpp3 | 6 | 0 | Todo | Read chapters 1-3, 5; understands what makes a forecast 'good'
Wk3-7 | SE | Designing Data-Intensive Applications (Kleppmann) — Ch.1-4, 7 | Book | Primary | Library | Brunel library / O'Reilly | 14 | 0 | Todo | Read Ch.1-4 + 7; can explain replication, partitioning, and serializability
Wk3-7 | SE | System Design Primer (donnemartin) | Repo | Backup | Free | github.com/donnemartin/system-design-primer | 6 | 0 | Todo | Read core sections; took notes on caching + load balancing
Wk3-7 | SE | 12factor.net — Twelve-Factor App | Article | Primary | Free | 12factor.net | 1 | 0 | Todo | Read all 12 factors; ARIS deployment audited against them
Wk3-7 | SE | roadmap.sh — Backend roadmap | Roadmap | Primary | Free | roadmap.sh/backend | 2 | 0 | Todo | Walked the roadmap; identified 3 gaps to patch via ARIS work
Wk11-13 | MATLAB | MATLAB Onramp (MathWorks) + Simulink Onramp | Course | Primary | Free | matlabacademy.mathworks.com | 6 | 0 | Todo | Both Onramp courses completed with certificate
Wk11-13 | MATLAB | MathWorks Vehicle Dynamics Onramp (if available) | Course | Backup | Free | matlabacademy.mathworks.com — search Vehicle Dynamics | 3 | 0 | Todo | Completed if available; otherwise built bicycle model in Simulink unaided
Wk10-12 | LLM | DeepLearning.AI short courses — RAG + LangChain | Course | Primary | Free | learn.deeplearning.ai | 6 | 0 | Todo | Completed RAG + LLM application short courses; built a toy RAG over docs
Wk10-12 | LLM | Anthropic Cookbook (GitHub) — RAG + tool use | Code | Backup | Free | github.com/anthropics/anthropic-cookbook | 3 | 0 | Todo | Adapted 1-2 cookbook recipes to ARIS narration prompts
Always-on | DSA | NeetCode 150 (Roadmap) | Course | Primary | Free | neetcode.io | 100 | 0 | Todo | 100 of 150 problems Done by August, 150 by application time
Always-on | DSA | Grokking Coding Interview Patterns (Educative) | Course | Backup | Paid (free trial) | educative.io | 30 | 0 | Todo | Patterns 1-12 read + 3 example problems each implemented
Always-on | DSA | CSES Problem Set | Practice | Backup | Free | cses.fi/problemset | 30 | 0 | Todo | Sorting + Searching section completed (used as alternative to LeetCode)
Wk16-17+ | Interview | Pramp — peer mock interviews | Practice | Primary | Free | pramp.com | 10 | 0 | Todo | Completed 5 behavioral + 5 technical mocks
Wk16-17+ | Interview | Interviewing.io — anonymous mocks | Practice | Backup | Free + paid | interviewing.io | 6 | 0 | Todo | Completed 3 mocks; reviewed feedback
Wk16-17+ | Interview | Cracking the Coding Interview (Laakmann McDowell) — behavioral chapters | Book | Primary | Library | Brunel library | 4 | 0 | Todo | Read behavioral + 'how the process works' chapters
Wk14+ | Quant prep | A Practical Guide to Quantitative Finance Interviews (Xinfeng Zhou) | Book | Primary | Library/PDF | Brunel library | 12 | 0 | Todo | Read brain-teasers + probability chapters; solved 30+ problems
Wk14+ | Quant prep | Heard on the Street (Crack) | Book | Backup | Library/PDF | Brunel library | 8 | 0 | Todo | Read first 100 puzzles; solved without looking at answers
Always-on | F1 strategy | F1: Beyond the Grid podcast (esp. strategy episodes) | Podcast | Primary | Free | Spotify / open.spotify.com | 10 | 0 | Todo | Listened to 8+ strategy-themed episodes
Always-on | F1 strategy | Bernie Collins on Sky F1 + The Race YouTube strategy briefings | Video | Backup | Free | youtube.com/@therace | 8 | 0 | Todo | Watched 1 strategy briefing per race week
Always-on | F1 strategy | Mark Hughes columns — The Race | Article | Primary | Free | the-race.com/author/mark-hughes | 4 | 0 | Todo | Read 1 column per race week; built strategy vocab notebook
Wk4+ | Writing | Julian Shapiro's writing guide | Article | Primary | Free | julian.com/guide/write | 2 | 0 | Todo | Read entirely; applied to LinkedIn post #2 onward
Wk4+ | Writing | Patio11 — Don't Call Yourself a Programmer | Article | Primary | Free | kalzumeus.com/2011/10/28/dont-call-yourself-a-programmer | 0.5 | 0 | Todo | Read; key lessons noted in Obsidian

## Applications
# | Company | Role | Type | Source | Date Applied | Status | Last Update | Days Since Apply | Days Since Update | Next Action | Next Action Date | Notes
1 | Williams Racing | Software Engineer — Vehicle Performance Software | Placement | Williams careers |  | Drafted
2 | Aston Martin F1 | Software Engineer — AMPT VP | Placement | AM careers |  | Drafted
3 | Mercedes AMG HPP | Software & Controls Placement | Placement | Mercedes careers |  | Drafted
4 | McLaren Racing | Engineering / Software Placement | Placement | McLaren careers |  | Drafted
5 | Red Bull Racing | Software / Race Strategy Student | Placement | RB careers |  | Drafted
6 | Williams Advanced Engineering | Software Engineer Placement | Placement | WAE careers |  | Drafted
7 | Red Bull Advanced Technologies | Software Placement | Placement | RBAT careers |  | Drafted
8 | M-Sport (Cumbria) | Software Engineer Placement | Placement | M-Sport careers |  | Drafted
9 | Alpine F1 | Software Placement | Placement | Alpine careers |  | Drafted
10 | AP Racing | Software / Engineering Placement | Placement | AP Racing careers |  | Drafted
11 | Bentley Motors | Software Engineer Placement | Placement | Bentley careers |  | Drafted
12 | McLaren Applied | Software / Telemetry Placement | Placement | McLaren Applied careers |  | Drafted
13 | Cosworth | Electronics / Software Placement | Placement | Cosworth careers |  | Drafted
14 | G-Research | Quantitative Researcher Internship | Internship | G-Research careers |  | Drafted
15 | Optiver | Software Engineer Internship | Internship | Optiver careers |  | Drafted
16 | IMC Trading | Software Engineer Internship | Internship | IMC careers |  | Drafted
17 | Jane Street | Software Engineering Internship | Internship | JS careers |  | Drafted
18 | Citadel / Citadel Securities | Software Engineer Internship | Internship | Citadel careers |  | Drafted
19 | Bloomberg LP | Software Engineer Placement | Placement | Bloomberg careers |  | Drafted
20 | Stripe | Software Engineer Internship | Internship | Stripe careers |  | Drafted
21 | Revolut | Software Engineer Internship | Internship | Revolut careers |  | Drafted
22 | Wise | Software Engineer Placement | Placement | Wise careers |  | Drafted
23 | Monzo | Software Engineer Placement | Placement | Monzo careers |  | Drafted
24 | Google UK | STEP / Engineering Practicum | Internship | Google careers |  | Drafted
25 | Meta UK | Software Engineer Placement | Placement | Meta careers |  | Drafted
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Formulas:
Days Since Apply = IF([Date Applied]="","",IF([Date Applied]>TODAY(),0,TODAY()-[Date Applied]))
Days Since Update = IF([Last Update]="","",IF([Last Update]>TODAY(),0,TODAY()-[Last Update]))

## Networking
# | Date Sent | Person | Company | Role | Connection | Channel | Action | Reply? | Reply Date | Days to Reply | Follow-up Date | Next Step | Notes
1 | [7 empty] | Pending
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Settings
ARIS Master Planner — Settings
Key Date | Value | Status Options | Tier | Time Category
Project Start (Week 1, Day 1) | 2026-05-04 | Todo | Core | ARIS
Phase 3 Brunel Kill | 2026-06-21 | Doing | Tier A | DSA
ARIS Ship Date | 2026-08-31 | Done | Tier B | App Tool
Applications Open (est.) | 2026-09-15 | Skipped | Tier C | Networking
Application Sprint End | 2026-11-30 | Blocked |  | Writing
Today | 2026-05-07 |  |  | Resources
Other
How this planner works
1. Open Daily Log every evening, log hours by category. Takes 60 seconds.
2. Update ARIS Tasks status as you tick them off. Dashboard auto-updates.
3. Update DSA Tracker after each problem solved.
4. Resources sheet — log hours and mark Done when verified.
5. Applications sheet — log every application Sept onwards.
6. Networking sheet — log every outreach + reply.
7. Press F9 (or Ctrl+Shift+F9) to recalculate if numbers look stale.
8. Charts on Dashboard auto-pull from underlying sheets.